MONITORING REPORT ON THE IMPLEMENTATION OF THE ACTION PLAN FOR THE NATIONAL STRATEGY “VISION FOR DEINSTITUTIONALISATION OF CHILDREN IN BULGARIA”

1 July 2013 – 30 June 2014

CONTENTS

1. Introductory part

А. Summary...............................................................................................................................1

Progress in implementation of the Action Plan         ................................................................1

Key achievements over the period............................................................................................2

Major problems and key recommendations..............................................................................5

B. Process organisation and leadership     ................................................................................6

# Interdepartmental Working Group   .........................................................................................6

# Steering Committee (expert group)...........................................................................................7

# Project Implementation Units ...................................................................................................9

# Regional Teams on Deinstitutionalisation ………....................................................................9

В Achievement of the objectives laid down the Action Plan ……….....................................10

2. Achievements and challenges in the implementation of the Action Plan

А. Progress in implementation of the projects laid down in the Action Plan…………… ....18

Project BG 051PO 001-5.2.08-001 „Childhood for All” ........................................................18

# Project BG 051PO001-5.2.10-0001 „DESTINATION: family” .............................................21

Project „I Have Family, Too” ................................................................................................ 24

Project BG051PO001-6.2.13 “Development of the system for social services planning and provision at the regional level” .,,,,,,,,,,,,,,,,,,...........................................................................26

Project BG051PO001-6.2.09 “Capacity Building of the Social Assistance Agency to improve the quality and effectiveness of social work” ………………………………..........28

Project BG161PO002-1.9.01-0001 “Support” ..................................................................... 30

Project “Development of Transnational Network for Supporting Children and Families and for Deinstitutionalisation of Child Care” ……………………………………....................................................................32

# Project BG051PO001 7.0.02-0003 „Change Management Through Experience and Knowledge” ...........................................................................................................................33

Project BG051РО001-4.1.07 „Inclusive Education” .............................................................34

Project „Social Inclusion” ...................................................................................................... 37

Project on deinstitutionalisation of children aged 3 to 18 placed in HCDPCs........................38

B. Legislative Changes Securing the Deinstitutionalisation Process.......................................39

C. Financial Means and Resources in the Deinstitutionalisation Process……........................41

D. Additional Resources in Support of the Deinstitutionalisation Process ........................... 48

# 3. Main Conclusions and Recommendations

A. Updating the Action Plan – shared approaches and principles ……………......................59

B. Sequencing of the OP activities for the next programming period ………………...............?

1. Introductory part

А. Summary

- Progress in implementation of the Action Plan

The fourth Monitoring Report on the progress of the deinstitutionalisation process in Bulgaria aims to render an account of the implementation of the Action Plan to the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” in the period from 01 July 2013 till 30 June 2014.

The report covers the achievements in the childcare deinstitutionalisation process and in the implementation of the Action Plan projects, the experience gained, the activities carried out and the initiatives taken. It describes the key results, conclusions and challenges and provides recommendations for future decisions and actions. The cooperation and coordination of all partners and stakeholders involved in the deinstitutionalisation process are an important element of the report.

In contrast to the third Monitoring Report, which was approved with a decision of the Council of Ministers of 18 December 2014,  the structure of this fourth report was changed in order to present the information in a more comprehensive way and to focus on the most important actions in the deinstitutionalisation process over the one-year review period. The new structure of the fourth Monitoring Report was approved at a meeting of the Interdepartmental Expert Working Group involving also representatives of the NGO sector.

The new structure of the report consists of three parts – introductory part, achievements and challenges in implementation of the Action Plan, and main conclusions and recommendations. The introductory part includes a description of the process organisation and leadership and highlights the achievements against the objectives laid down in the Action Plan, as well as the related problems and challenges. The second part includes a report on implementation of the deinstitutionalisation process related projects, the legislative changes concerning the process, the financial means and the additional resources invested in support of the childcare deinstitutionalisation process in Bulgaria. This part contains a report on the activity of non-governmental organisations and includes a quick review and assessment of the process by an independent external expert. The third part deals with the process outlook and covers the matters concerning the adjustment of the Action Plan and the sequencing of the operational programmes’ activities in the next programming period. Finally, the attachments to the report contain information on each one of the Action Plan projects.

The analysis of implementation of the activities and measures in the Action Plan shows that the Plan is in its final stage of implementation. The Project Implementation Units took steps for extension of the implementation deadlines in view of maximum achievement of the objectives laid down in the Plan and absorption of the project allocations.

The current review period, like the previous one, was again marked by changes in the country’s executive power which affected the implementation of the specific projects, as well as the overall deinstitutionalisation process. This period, characterised with political challenges, coincided with the most decisive phase of the process – the transfer of the children and youths from the institutions and their adaptation in the new services. The municipalities which are entrusted with the organisation of the care for children and youths with disabilities, showed different degrees of preparedness to launch the provision of the social services planned. This was one of the main deinstitutionalisation challenges in the review period.

In order to implement the projects in the Plan in an effective and efficient manner and to bring them to successful completion, as well as in light of planning properly and ensuring continuity in the absorption of EU funds in the 2014-2020 period, the Action Plan needs to be updated. Such a step would ensure achievement of the 2025 horizon  objectives set out in the Vision.

Another major factor, which brings into play the need to refocus the priorities of the Action Plan’s strategic objectives, is the fact that despite of the permanent downward trend in the number of children raised in specialised institutions and separated from their biological families, this number remains significant. A change is needed, with emphasis on prevention and family support in accordance with the UN Guidelines on Alternative Care, with parallel further closing of specialised institutions and enhancing the capacity of the new community-based services. This is the main conclusion of the quick review and assessment of the Vision’s and Action Plan’s implementation, conducted by an independent international consultant.

- Key achievements over the period

It is expressly recommended in the previous Monitoring Report that, in connection with the political changes in the country, “the operation of the Interdepartmental Working Group on deinstitutionalisation must resume at top political level in order to ensure continuity of the process and taking of correct and adequate decisions”. Highlighted is also that “an Expert Working Group must be set up and start functioning in order to support and assist the Interdepartmental Working Group with motivated decision-making”. These recommendations were taken into account and, over the review period, the Interdepartmental Working Group convened four times and the Interdepartmental Expert Working Group involving representatives of the NGO sector became operational and convened twice.

The downward trend in the number of children placed in specialised institutions persisted in the review period. Total 2 691 children were raised in the operational specialised institutions at 30 June 2014. By way of comparison, 3 592 children were placed in institutions as of 30 June 2013. Over a year, within the review period, the number of children placed in institutions decreased by 901 children or 25%.

Over the period, the number of specialised institutions decreased by 8 – 7 homes for children deprived of parental care (HCDPC) and 1 home for medical and social care for children (HMSCC) were closed. The children from those institutions were provided family or close to family environment enabling their individual development and social integration.

An advance in the development of foster care is registered in this period as well. The option of bringing up and educating a child in a foster family is becoming more recognised by the society and the interest and desire of candidate foster families are growing.

The analysis of foster care development shows that some of the problems and challenges typical for this social service have been successfully addressed:

- The public attitude to children raised in specialised institutions and to foster care as an alternative to institutional care has changed;

- The interaction of all actors in foster family selection, evaluation and approval  – municipalities, Social Assistance Directorates (SAD) and NGOs – was improved;

- The public awareness of foster care as a community based social service was raised, etc.

Significant progress is observed also in the development of community-based social services for children. The number of services opened as activities delegated by the state has increased – new 33 community-based social services for child and family support with a total capacity of 632 places were opened over the review period.

The main achievements in the field over the review period could be summarised as follows:

- the uniform cost standards applicable to the financing of services were increased in 2014;

- the number of new community based supporting services is prevalent, at the expense of the residential ones;

- a network of Community Support Centres (CSC) is developing, indicating a need of a social service which works with the children and families at risk and provides complex support to them.

Over the review period, the deinstitutionalisation of children with disabilities entered its most significant stage – the transfer and adaptation of children aged 3+ and youths from Homes for Children with Intellectual Disabilities, the Home for Children with Physical Disabilities (HCPD) and HMSCC in new residential services was launched. 32 Centers for Family-type Accommodation (CFTA) and 6 Protected Homes (PH), built and opened in 19 of a total of 80 municipalities, became operational within the Operation „Don’t Leave a Child Out”.

The handing over of care for children and youths by the specialised institutions encountered many difficulties and highlighted serious challenges. Despite that, 267 children and youths with disabilities were successfully taken out and placed in the new services within the review period. Addressing the challenges highlighted the needs of the municipalities which became responsible for the children and youths with disabilities. The change in the form of care yielded its first results towards improved general status of users, both physically and emotionally.

In November 2013, the target group of the Operation “Don’t Leave a Child Out” was enlarged to cover all children and youths placed in HCDPC, including children and youths with disabilities. The State Agency for Child Protection (SACP), in partnership with the Social Assistance Agency (SAA), developed and implemented a needs assessment mechanism for those children and youths informing the decisions for their referral to new resident-type services. Thus, measures for deinstitutionalisation of the children placed in HCDPC were included in the scope of the Operation.

Ministry of Health’s (MH) decisive actions with regard to the deinstitutionalisation process continued in this review period. Data show that placements in HMSCC have been reduced. Of relevance is the fact that 18 Day Care Centres (DCC) providing health services for children with physical and/or intellectual disabilities raised in a family environment who need daily rehabilitation and physiotherapy were opened over the period on the territory of HMSCC. The restructuring of 8 pilot HMSCC across the country is going on within the project “DESTINATION: family”.

As far as the legislative changes are concerned, of relevance is the fact that a differentiated approach was prepared over the review period and will take effect from 2015 in setting the financial standards applied by municipal budgets for the Centers for Family-type Accommodation, Protected Home and Day Care Centre social services which are activities delegated by the state.

A Methodological Manual on provision of the Family Type Placement Centre for Children and Youths service was developed during the period in view of initiating quality services tailored to the actual needs of flexibility of provision.

The non-governmental organisations have important input. Over the review period, they cooperated fully with the governmental institutions and the local authorities, as well as with the Project Implementation Units (PIUs) of the Action Plan projects. This functioning cooperation provided real support in addressing the community based challenges. The NGOs provided  assistance in the form of different activities to their colleagues managing the new services and delivering child care. Thus, good partnerships developed at the local level between representatives of the central administrations, the municipalities and the non-governmental sector, aimed at improving the quality of life of children and youths.

- Major problems and key recommendations

Process management and partnership

The implementation of activities for deinstitutionalisation of childcare in Bulgaria requires a deeper and coherent approach, good absorption of the available resources and continuity.

In that light, the successful structuring of community based social services so that they can replace institutional care on a permanent basis implies strong ownership and partnership between the bodies, institutions and organisations involved at the central and the local level – Ministry of Labour and Social Policy (MLSP), SACP, SAA, MH, Ministry of Education and Science (MES), municipal and regional administrations, NGOs. There is still much to be done in order to improve the coordination of activities and the forms of communication between the different actors engaged in the general deinstitutionalisation process.

Support for the new social services

The need to continuously improve the capacity of the staff employed in the new social services is on the agenda. The underprepared teams at the launch of the CFTA and PH services and the related high turnover pose serious challenges to the smooth development of the deinstitutionalisation process. The provision of adequate expertise for the teams by different stakeholders and the availability of a sufficient number of supporting services in all municipalities with operational CFTA and PH are key factors for ensuring the sustainability of the process. Besides, supervision needs to be provided on a regular basis.

Expertise building needs to be encouraged in order to establish a system of support, partnership and exchange of good practices and information among the teams in the new services.

Financial mechanisms

Steps need to be taken to modify the model of planning and reporting of government transfers in view of more flexible financing of social services.

There is lack of a financial mechanism ensuring reallocation of funds from the existing specialised institutions to the new services developed under the projects.

At the end of the review period, the uniform financial standard for the provision of the foster care service is not developed yet, but steps have been taken to that effect.

Integrated services

There is a need to develop a model for provision of integrated health and social services for children with severe disabilities who need medical care as a matter of priority and for children with intellectual disorders. The models have to be guaranteed by ensuring their legal regulation and securing the financial resources for them. Towards the successful implementation of the models, the healthcare system will have to organise work locally so that the needs of the children and youths with disabilities transferred from the specialised institutions are adequately met.

The absence of legal regulation of such type of services impedes the successful restructuring of the pilot HMSCC.

Improving the coordination of the local administrative structures and the central units with regard to the access of children with disabilities to education and ensuring the best possible conditions of education for each child depending on their state of health.

B. Process organisation and leadership

- Interdepartmental Working Group

Children’s transfer from the specialised institutions is a process which calls for taking important political and strategic decisions at a high management level.

Pursuant to the childcare deinstitutionalisation policy implemented through the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria”, the Action Plan for implementation of the Strategy provides for setting up an Interdepartmental Working Group to manage and coordinate the process. The group’s major commitments concern the overall implementation of the Plan, the monitoring, evaluation and coordination of the specific activities and policies. The Interdepartmental Working Group is a major partner of the European Commission for communicating and coordinating the decisions planned.

It is expressly recommended in the previous Monitoring Report that, in connection with the political changes in the country, “the operation of the Interdepartmental Working Group on deinstitutionalisation must resume at top political level in order to ensure continuity of the process and taking of correct and adequate decisions”.

In that light, an Interdepartmental Working Group on management and coordination of the deinstitutionalisation process, chaired by a vice-premier, was set up with Order No. P-205/11 October 2013 of the Bulgarian Prime Minister. The Interdepartmental Working Group is chaired by the line vice premier who is deputized by a deputy minister of labour and social policy and the president of the State Agency for Child Protection. The working group members include the line deputy ministers of: regional development and public works, education and science, health, agriculture and food, finance, as well as representatives of the Administration of the Council of Ministers, the National Association of Municipalities in the Republic of Bulgaria /NAMRB/ and State Fund “Agriculture”.

In the period from 1 July 2013 till 30 June 2014, the Interdepartmental Working Group convened four times (on 25.10.2013, 22.11.2013, 20.12.2013 and 27.06.2014) to discuss the implemented and the future activities of the deinstitutionalisation process. The third Monitoring Report covering the implementation of the Action Plan in the period from 01 July 2012 till 30 June 2013, the key achievements, initiatives and results and the coordination of all process actors was approved. A decision for differentiating the financing of social services and setting up an interdepartmental expert working group to support the coordination and implementation of the Action Plan of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” tasked to provide direct monitoring of the activities was discussed and taken at this level. As recommended by the Interdepartmental Working Group, an independent evaluation of the deinstitutionalisation process was carried out with the participation of an international consultant and with the support of UNICEF Bulgaria. On the basis of the analysis of the progress in the process, a decision to update the Action Plan was taken. The last meeting of the Interdepartmental Working Group for 2013 was held in a home for children deprived of parental care where the members met with the children and the staff of the home.

In the context of the changes which occurred in the executive authority, it is critical to update in due time the membership and the functions of the Interdepartmental Working Group with a view to ensuring continuity and sustainability of the deinstitutionalisation process and guaranteeing respect of the rights of children.

- Steering Committee (expert group)

In view of the implementation challenges of the deinstitutionalisation process and in light of the activities laid down in the 5 Action Plan projects , inter-institutional cooperation and targeted efforts by all institutions engaged at national, regional and local level continue, contributing to an effective process. It should be highlighted again that the interaction of all stakeholders, who are actively involved in identifying the key tasks, measures, expected results and the target groups addressed by the deinstitutionalisation process, is essential for the implementation of this policy. Ensuring sustainability is directly linked to providing expertise to inform strategic and political decision making.

Therefore, the need that “an Expert Working Group must be set up and start functioning in order to support and assist the Interdepartmental Working Group with motivated decision-making” is highlighted as a key recommendation in the previous Monitoring Report.

An Interdepartmental Expert Working Group with a permanent mandate was set with  Order No. Р-249/ 28 November 2013 of the Prime Minister in the review period to support the coordination of the activities in the Action Plan of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria”.

The working group is co-chaired by the president of SACP and the line deputy minister of labour and social policy. The members include representatives of the responsible institutions involved in the deinstitutionalisation process – MLSP, MH, MRDPW, MAF, MES, SACP, SAA, as well as representatives of NAMRB, UNICEF, and the managers of all Action Plan projects.

A mechanism to select 5 non-governmental organisations to be included as members in the working group was developed and implemented with a view to achieving  effective coordination with the representatives of the NGOs operating in the field of childcare deinstitutionalisation. The guiding motive in designing the mechanism was the desire to create a maximum transparent procedure which enables the involvement of non-governmental organisations. Five non-governmental organisations were nominated on the basis of the selection and became memebrs of the expert working group. These are Cedar Foundation; BAPID – Bulgarian Association of People with Intellectual Disabilities; National Network for Children; Pedagogical and Social Support for Children FITSE – Bulgaria; Lumos Foundation. Pursuant to the activities laid down in the Action Plan, the group developed and approved at a meeting its internal Rules of Procedure.

The expert group has a mandate to monitor the implementation of specific activities in the Action Plan and to monitor and evaluate the Plan’s implementation. Its main task is to provide coordination of the governmental institutions, other organisations and all projects related to childcare deinstitutionalisation.

In the period 30.06.2013 – 01.07.2014, the Interdepartmenta Expert Working Group convened twice (on 14.02.2014 and on 11.04.2014 г.) to discuss the key achievements and major challenges of implementation of each project in the Action Plan, the coordination and communication in the deinstitutionalisation process, the creation of supporting environment for education of children with disabilities using resident-type services, and the enlargement of the target group of the Operation “Don’t Leave a Child Out”.

The deinstitutionalisation process is currently in its critical phase. The operation of the Interdepartmenta Working Group, as well as placing major problems and challenges on the agenda and taking adequate decisions on a timely basis are essential for the management and coordination of the activities for transferring children from the specialised institutions and ensuring the quality of the new social services.

- Project Implementation Units

At the launch of the Action Plan projects, project implementation units (PIU) were set up. There is continuous contact between the units and the Contracting or Managing Authority of the respective operational programmes within which the projects are implemented. Over the review period, all PIUs operated in a volatile political environment of changing governments and early parliamentary elections. These critical circumstances affected to some extent the projects’ implementation. Maximum efforts were made to implement the activities according to schedule.

Due to the importance of the different activities related to the deinstitutionalisation process, PIU submitted applications for extension of the respective projects.

The meetings of the teams of the Action Plan projects were carried out with the assistance of Project „Support”. The five events (31.07.2013, 26.09.2013, 16.10.2013, 26.11.2013, 30.01.2014) were aimed and synchronising and coordinating the activities within the deinstitutionalisation process. They provided a forum for sharing difficulties and problems, need of assistance and support, inter-institutional communication, and good practices. Taking joint specific decision on the issues raised yielded specific results towards improved child welfare.

With a view to improving the interaction of the different PIUs, 10 meetings were held on specific occasions between representatives of the Project “Support” and different Action Plan projects. Between January and June 2014, the leaders of the projects in the Plan exchanged information also during workshops organised by Project “Support”.

With a view to improving the coordination and communication in the deinstitutionalisation process, it is necessary to focus on the increased interaction of all administrative structures implementing projects under HRD OP, RD OP and RDP.

It is also necessary to make analytical reviews of the projects, to identity the problems and to find ways to address them.

- Regional Teams on Deinstitutionalisation

The structures at the regional level – the Regional Teams on Deinstitutionalisation (RTD) – have a critical role to play. Their activity is detailed in the previous Monitoring Reports which describes also the experience gained.

The 28 RTDs in each administrative region remain operational. They include one representative each of the Regional Directorate for Social Assistance (RDSA), the Regional Health Inspectorate (RHI) and the Regional Inspectorate of Education (RIE).

The main functions of the RTD representative include:

- Keeping track of the overall process of deinstitutionalisation at regional level;

- Providing support for improving the interaction, coordination and communication of the teams of the Action Plan projects of the National Strategy Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” at regional / municipal level;

- Providing assistance and methodological support to regional / municipal authorities in setting up, developing and establishing the new social services;

- Creating and expanding the contacts between all stakeholders at regional level.

Problems related to the replacement of team members were identified over the review period. Despite the turnover, the teams continued to discharge their functions of a major link between the central administrations and the local communities and to provide the necessary support in view of guaranteeing the best interest of every child and youth.

Monitoring of the transfer of children and youths from institutions and their adaptation in the new services was provided with the active support of the regional teams. The RTDs had a decisive input in the closure of institutions and in introducing and building alternative and innovative community based services – the key focus of the deinstitutionalisation process in the review period.

The regional structure set up creates conditions for identifying problems and difficulties and offers different variants for addressing them on the basis of the local expertise and administrative resource. The role of RTD is essential for the horizontal and vertical coordination and communication between all process actors and in this since it is critical for the success of the overall deinstitutionalisation process. There is a need to design a mechanism enabling the teams to remain operational after the closure of Project “Support”.

NGO representatives and a wide circle of deinstitutionalisation process stakeholders can be involved in the design of such mechanism.

C. Achievement of the objectives laid down in the Action Plan – overall results

- Develop a system of family and community-based services across the country which exclude existence of specialized institutions for children – major achievements and challenges

The National strategy for deinstitutionalisation of the children sets out strategic objectives for guaranteeing the children’s right to live in a family environment and receive quality care and services according to their individual needs.

Ensuring the right of children to live with their parents is a priority of the reform of child care. Efforts are focused on improving the good and responsible parenting skills and changing the attitude to the child. A set of parental support measures have been implemented, such as social, financial and psychological assistance, including temporary (daily, weekly) care for the child in order to prevent his/her abandonment. Specific parental support mechanisms reflecting the changes in the forms and organisations of family life in Bulgaria and the increasing mobility of family members are developed. The family environment and the contact with the parents is essential for the development of the child.

Preventing the abandonment and placement of children in specialised institutions is a priority of the state policy in the field of child protection and is focused on decreasing the number of children placed in specialised institutions and on guaranteeing their right to grow up in a family or close to family environment.

Evidence shows that the activities implemented have helped decrease notably the number of children raised in institutions. Placements in institutions have also been reduced – the number of children being placed therein is decreasing.

At 30.06.2014, total 2 691 children and 571 youths were placed in the specialised institutions for children, as follows:

- 196 children in 11 Homes for Children Deprived of Parental Care aged 3 – 6 years;

- 1 039 children and 78 youths in 39 Homes for Children Deprived of Parental Care from I to XII grade;

- 358 children and 487 youths in 23 Homes for Children with Intellectual Disabilities;

- 11  children and 6 youths in the Home for Children with Physical Disabilities;

- 1 087 children in the Homes for Medical and Social Care for Children.

In 2013, 2 778 children were accepted in the HMSCC system, including 1104 with disabilities. In the first six months of 2014, 2 059 children, including 956 with disabilities were accepted.

Notable is the upward trend in the number of children in the community using the services of the day care centres at HMSCC – they have increased by about 17% over a year.

The downward trend in the number of children placed in institutional care persists, resulting from the implemented strategic documents and deinstitutionalisation projects, including foster care development and increased number of centres for family-type accommodation for children with disabilities as an alternative family environment option.

The most successful measures resulting in notable decrease in the number of children placed in specialised institutions are the measures for prevention of abandonment, for reintegration, placement of children in families of relatives or close friends, and adoption.

| Year Activity | 2010 | 2011 | 2012 | 2013 | 2014 (till July inclusive) |
| --- | --- | --- | --- | --- | --- |
| Complaints, applications for assistance, alerts | 43 458 | 48 549 | 35 660 | 35 409 | 20 401 |
| Work towards prevention of abandonment | 3 660 | 5 005 | 4 332 | 4 554 | 2700 |
| Successfully closed prevention cases | 1 193 | 1 456 | 1 932 | 3 137 | 1626 |
| Reintegration cases | 2 432 | 2 135 | 2 088 | 2 361 | 1096 |
| Successfully closed reintegration cases | 1 534 | 1 423 | 1 834 | 1 329 | 700 |
| Children placed in families of relatives or close friends | 1 461 | 1 623 | 1 858 | 1 577 | 740 |
| Adopted children | 950 | 952 | 739 | 737 | 397 |

Foster care is a major alternative to the placement of children in specialised institutions. An important objective of the foster care provided by professional foster families is to support the deinstitutionalisation process by offering an alternative to institutional placement. Over the review period, the development of the foster care social service was very dynamic – the service is successfully provided, the number of candidates for foster parents increases and so does the number of recognised foster families and of the children placed therein. An important role in that light has the project “I Have Family, Too” implemented by SAA.

| Year Activity | 2010 | 2011 | 2012 | 2013 | 2014 (till July inclusive) |
| --- | --- | --- | --- | --- | --- |
| Children placed in foster families | 221 | 391 | 839 | 1 441 | 767 |
| Approved voluntary foster families | 42 | 61 | 63 | 25 | 5 |
| Approved professional foster families | 210 | 334 | 583 | 756 | 298 |

For the development of foster care it is necessary to mobilise the public at local, regional and national level, as well as all governmental and non-governmental institutions  for improving the quality and scope of the service as an alternative family environment for children who, for whatever reason, cannot be raised in their families.

The set up of an Interdepartmental Working Group is planned, tasked to design a financing standard for the foster care social service as an activity delegated by the state. The work of the group will be kicked off after the end of the review period (October 2014).

The community-based residential social services initiated within the Operation “Don’t Leave a Child Out” became operational on 1 September 2013: 22 children and youths with disabilities were placed in two centers for family-type accommodation.

Over the review period, total 267 children were placed in the new services (FTPC and PH) initiated in 19 municipalities:

- 234 children and youths are placed in FTPC in total 25 municipalities – Asenovgrad, Vidin, Gabrovo, Gorna Oriahovitsa, Gotse Delchev, Karnobat, Montana, Pernik, Plovdiv, Ruse, Silistra, Sozopol, Stamboliiski, Targovishte, Harmanli, Cherven Briag and Yambol;

- 33 youths are placed in PH in 6 municipalities – Aitos, Vidin, Montana, Plovdiv, Cherven Briag and Yambol.

The team of the project “Childhood for All” designed a system for feedback on the adaptation of the children and youths placed in the new services. The teams that took up the care for the children from the institutions did encounter many difficulties. SACP looks for different opportunities to support the providing municipalities in their efforts to offer quality care in their services. Apart from the basic training included in the project, additional supporting trainings on the transfer of children from the specialised institutions to the services and on the organisation of work in FTPC and PH were organised for the service teams in cooperation with Lumos Foundation and Cedar Foundation.

Over the review period, 18 day care centres on the territory of HMSCC, providing health services for children with physical and/or intellectual disabilities raised in family environment who need daily rehabilitation and physiotherapy, continued operations. The day care centres offer diagnostics of the somatic, mental, neurological, intellectual and speech development of the children, design of individual programmes for complex medical and psycho-educational rehabilitation, design of programmes for working at home, speech therapy exercises, individual and group psychotherapy, rehabilitation and physiotherapy procedures; training of parents to carry out rehabilitation at home in support of the therapy, training of candidate adopters, consultations for the parents of children with special needs. At the end of June 2014, 581 children use free the services of the Day Cares Centres at HMSCC for children with disabilities.

The number of community based social services initiated as state delegated activities increased in the period 01.07.2013 - 30.06.2014.

| Type of service | Number of new services initiated | Capacity | Cost per used (in BGN) |  | Cost value (in BGN) |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 |  |
| Centre for Family-Type Accommodation | 8 | 92 | 7981 | 8304 | 747 818 |
| Community Support Centre | 13 | 340 |  | 2865 | 970 110 |
| Centre for Social Rehabilitation and Integration of Children | 3 | 58 | 2561 | 2599 | 149 488 |
| Crisis Centre | 2 | 18 | 7931 | 8251 | 148 518 |
| Day Care Centre for Children with Disabilities / Week Care Centre for Children with Disabilities (WCCCD) | 4 | 80 | 5768 5933 | 5855 6022 | 468 220 |
| Centre for Working with Children in the Street | 1 | 30 | 6582 | 6681 | 200 430 |
| Transitional Homes for children | 2 | 14 | 6486 | 6748 | 92 376 |
| Total for all BGN 2 776 960 |  |  |  |  |  |

Unfortunately, despite the efforts of the deinstitutionalisation process actors, the number of children taken out of their biological families and placed in alternative care – families of relatives or close friends, foster families, residential social services – is not small. This proves that the current measures in support of children and families need to be improved and developed with a view to achieving the desired effect.

- Close systematically all residential institutions for children in Bulgaria and guarantee long-term and short-term placement in family-type care for every child – major achievements and challenges;

Governmental efforts to close the specialised institutions for children have led to significant changes in a long term perspective. The number of institutions is on a permanent downward trend: 62 specialised institutions for children were closed from 2001 till 30 June 2014.

At 30 June 2014, there were 103 specialised institutions for children in Bulgaria:

- 29 homes for medical and social care for children (HMSCC) managed by the Ministry of Health;

- 23 homes for children with intellectual disabilities (RICID) managed by municipal authorities;

- 1 home for children with physical disabilities and preserved intellectual abilities (HCPD), managed by a municipal authority;

- 50 homes for children deprived of parental care (HCDPC) managed by municipal authorities.

As a result of the joint actions taken by the institutions engaged in the deinstitutionalisation process and their NGO partners,  8 specialised institutions for children were closed over the review period.

Seven homes for children deprived of parental care were closed:

- HCDPC “A. G. Kodzhakafaliata” – Burgas, from 01.09.2013;

- HCDPC – Omurtag, Targovishte District, from 01.09.2013;

- HCDPC “Hisarlaka” – Kyustendil, from 01.09.2013;

- HCDPC “Hr. Botev” – Novo Selo, Vidin District, from 01.09.2013;

- HCDPC – Popovo, Targovishte District, from 01.02.2014;

- HCDPC ‘St. Ivan Rilski” – Sofia, from 01.02.2014;

- HCDPC “Rada Kirkovich” – Plovdiv, from 01.03.2014.

HMSCC in Kyustendil was closed on 29 July 2013 on the basis of an established permanent downward trend in the number of children placements in the past few years. The main reason is that placements in the institution have been reduced by the local child protection structures. The last child left the home on 15 June 2013.

Within the action plan for the project “Childhood for All” designed in May 2014, 15 specialised institutions for children with disabilities were identified with a view to making a proposal for their closure by the end of 2014. Within that period the children and youths placed in the identified RICID will be taken out.

At the end of June 2014, SACP deposited in SAA a reasoned proposal for closure of RICID “St. Ekaterina” in the village of Iskra, Karnobat Municipality, RICID Targovishte and RICID Kosharitsa.

- Develop the legal and regulatory framework needed to support the transition to family and community-based care – major achievements and challenges;

# The mechanism for provision of social services needs to be changed in order to support the transition to family and community based care, improve the financing and management system and enhance the effectiveness and efficiency of social services. With a view to implementing the regulatory changes in the field, an Interdepartmental Working Group with wide representation of all stakeholders was set up to draft the Social Services Act with an order of the Minister of Labour and Social Policy of 02.04.2014. This is in full harmony with the reform launched which is directed towards deinstitutionalisation of care, modernisation and development of integrated cross-sector services and maximising their accessibility through mobility and flexibility.

- Improve the efficiency of the care system for vulnerable children and their families – major achievements and challenges.

Methodological Manual on Provision of the Social Service „Center for Family-Type Accommodation for Children and Youths”, which is among the planned community-based social services as an alternative of institutional care was developed in 2013 with a view to initiating quality services satisfying the actual need of provision flexibility. The approval of the methodological manual enables the placement of both children and youths in the family-type placement centres planned within the deinstitutionalisation process.

At the same time, an inter-institutional working group was set up with an order of the Minister of Finance of 19.09.2013 to develop a mechanism for re-allocation of the resources released from institutional care to community based care for children at risk and their families. The purpose is not only to initiate new community-based social services but also to guarantee their sustainability after ending the child care deinstitutionalisation projects being implemented.

In the period June – October 2013, under the Childhood for All Project, the staff of all specialised institutions included in the project’s target group was provided with organised group supervisions and trainings on preparing children and youths with disabilities for transfer from the institutions, organised by civil company “BAPID – FITSE”.

The trainings and supervisions of the teams employed in the new residential services for children and youths started in June 2013. At 30 June 2014, the planned basic training of staff in the new services has been provided in 35 municipalities to 291 individuals.

In order to improve child protection system’s effectiveness in working with vulnerable groups of children and their families, the staff of the Social Assistance Directorates across the country received the following trainings:

- Upgrading training of the staff in the Child Protection Departments under Project “Capacity Building of the Social Assistance Agency for Improved Quality and Efficiency of the Social Work”, from December 2013 till September 2014 – total 789 staff members, on the topics:

  - Methods for working with children – victims of violence, and their families;

  - Foster care – alternative form of raising children in family environment – process and specifics;

  - Methods for management of child at risk cases;

  - Methods for early diagnostics of the risk of child abandonment and prevention of abandonment;

  - Working with children – victims of traffic, and their families;

  - Methods for working with children – victims of violence, and their families.

- Parental alienation casework and applying the Methodological Guidance on working on cases of children at risk of parental alienation – 10 trainings.

- Training by the representation of the UN High Commissioner in Bulgaria on topics connected with the increased migration flow of asylum seekers – adults and children in Bulgaria – 15 trainings.

- Crime prevention among the vulnerable groups. Models of safe behaviour of social workers - 8 trainings.

- Social assistance for third country nationals in need of asylum and protection – 5 trainings.

- European practices for risk assessment and safety planning in the protection of victims of violence  – 11 trainings.

- Module training “Social work for children and families at risk” – 15 trainings on the following topics:

- Modern social policy for social work with children and families at risk

- Social services for children in the deinstitutionalisation process

- Social casework – needs assessment

- Models of safe behaviour of social workers

- Social worker’s work with children and youths with deviant and delinquent behaviour

- Children violence casework

- The social worker in a school for parents

2. Achievements and challenges in the implementation of the Action Plan

А. Progress in implementation of the projects set out in the Action Plan

Over the review period the projects in the Action Plan for implementation of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” entered their final stage which coincided with the crucial moment in the deinstitutionalisation process – transferring children and youths from the specialised institutions and their adaptation in the new services. In that light, measures to enhance the coordination of projects were taken, new activities and sub-activities were added to some of them, steps to extend the validity of  projects within the relevant operational programmes were taken. The above steps were called for by the dynamic situation, the need to address the difficulties, and in view of the best interest of the child. The teams of the Action Plan projects used their best efforts to do their job in a dynamic environment, volatile political situation and changes in the executive in order to achieve as well as possible the objectives laid down in each project.

- PROJECT BG 051PO 001-5.2.08-001 „Childhood for All”

Project „Childhood for All” is implemented by the State Agency for Child Protection with funding from Human Resources Development Operational Programme. Project partners are the Social Assistance Agency and the Ministry of Health. The project is part of Operation “Don’t Leave a Child Out” and was launched in 2010 with a duration of 54 months – 02.06.2010 - 02.12.2014. The project budget is BGN 4 960 400,17, including BGN 4 216 340,14 from the European Social Funds and BGN 744 060,03 from the national budget.

The purpose of the project is to change the philosophy of care for children with disabilities in Bulgaria by planning and implementing specific measures, effective in the long term, for real deinstitutionalisation of the children with disabilities placed in institutions for children.

The main efforts are focused on preparing and transferring the children with disabilities from the institutions by applying an individual approach to the needs of every child, identifying the necessary community-based social services and the respective target areas where they should be initiated, creating conditions for active involvement of stakeholders, engaging the local communities and enhancing the citizen participation in the processes of support and social inclusion of the children from the specialised institutions.

The transfer of the children and youths from the institutions to the new residential services started in reality in the review period 01 July 2013 – 30 June 2014. The first two FTPC in Karnobat Municipality became operational from 1 September 2013. At 30 June 2014, total 267 children and youths are placed in the new services (FTPC and PH) in 19 of the 80 target municipalities.

Over the review period, the target group of the project was enlarged to include the children from the Homes for Children Deprived of Parental Care (HCDPC). The enlargement was validated with a decision of the Monitoring Committee of HRD OP of November 2013. This change has been called for by the fact that at this stage the capacity of the residential services planned for initiation is greater than the number of children and youths from RICID and HMSCC.

In that light, in May 2014 multidisciplinary teams comprising different experts made, with the exclusive assistance of the Child Protection Departments, assessment of all 1 197 children (207 with disabilities and 990 without disabilities) from HCDPC. An adequate residential service was identified for every child as a result of the assessment.

In December 2013, after concrete steps had been taken for transferring the children from the institutions to the new residential services, it became evident that the measures and activities initially planned under the project were insufficient. Taking into account that the preparation of every child and youth for transfer is essential for their adaptation and for reducing the traumatic effect of separation and fear of change, SACP took steps to address the difficulties, including by additional trainings for the staff, supervision, strengthening the teams with further experts. The basic training of the staff of the new services planned under the project was provided in 35 municipalities to 291 individuals. 36 group supervisions of 463 individuals were carried out by 30 June 2014. All trainees and the municipal experts report a need of further supervisions and trainings.

NGOs experienced in the provision of services for children with disabilities were involved to help with their adaptation – agreements were signed with UNICEF. Cedar, Lumos, Child and Space, Hope and Homes for Children. All they provide their expertise free. Building on the experience from these partnerships, an agreement was reached on the development of a common local action framework and a mechanism for sharing good practices among the actors in the child care deinstitutionalisation process.

Over the review period, the opportunity for signing a cooperation agreement with Coalition “Childhood 2025”, of which leading NGOs involved in the deinstitutionalisation process are members, for provision of additional support to the municipalities was discussed. An action plan laying down specific measures with which the NGOs operating in the field of child care deinstitutionalisation will support  the process according to the available resources and expertise will be prepared for the agreement.

Amendments were made to project activity 5 “Motivation and awareness raising of local stakeholders concerning the positive effects of the deinstitutionalisation” which envisages organisation and holding of six regional meetings for exchange of experience and good practices for the providers of the new services for children and youths.

A Practical Manual on working with children from specialised institutions and their parents was published to help the teams of the new services and the municipalities in providing care for those children.

As mentioned earlier, 15 specialised institutions for children with disabilities were identified over the review period to be proposed for closure by the end of 2014. Identified were 512 cases of children and youths for whom the assessments regarding the type of residential service and settlement where they should be placed needed to be updated. A mechanism for holding conferences on cases was designed and multidisciplinary teams were set up. In the period June – August 2014, conferences were organised in all specialised institutions and the assessments of the children/youths were updated.

In June 2014, SACP deposited in SAA a reasoned proposal for closure of RICID “St. Ekaterina”, Iskra village, Karnobat Municipality, RICID Targovishte and RICID Kosharitsa.

Steps to update the National Map of Residential Services for Children/Youths with Disabilities were taken at the end of the review period. The changes concern the transformation of PH to which no or insufficient number of users are referred, in accordance with the needs of the local community.

Two of the three films planned under the project were made, with focus on the life of children with disabilities placed in institutions, the reasons for their abandonment by their parents, their dreams and the change in their life after they have left the institution. The films have been broadcast on national and regional televisions and are distributed among stakeholders on electronic carriers, shows are organised during public events.

Significant changes occurred in the target group of the project in the period from project start till 30 June 2014. 264 children were adopted. 60 children were reintegrated into their biological families, but it should be noted that there are 2 cases of unsuccessful reintegration. 51 children are placed in foster families. Two youths have left RICID after they have reached the age of majority. 6 children from RICID are placed in transitional homes and the same number of youths are transferred to Social Vocational Education and Training Centres (SVETC). 39 children are transferred to HCDPC, 44 youths are placed in Home for Adults with Intellectual Disabilities (HAID). Total 67 children and youths are placed in new residential services which are not part of those planned under the project. It should be pointed out also that from the project start in the summer of 2010 till 30 June 2014, 102 children and youths with severe disabilities placed in the homes for medial and social care for children and the homes for children with disabilities died.

At 30.06.2014, the number of children and youths from the initial target group of the project is 1 220, they are placed in 23 RICID, 1 HCPD and 29 HMSCC.

Over the review period, steps to extend the project validity till 30 June 2015 were taken.

- PROJECT BG 051PO001-5.2.10-0001 „DESTINATION: family”

Project „DESTINATION: family” is implemented by the Ministry of Health under Human Resources Development Operational Programme 2007-2013 since October 2012. The project duration is 34 months. At May 2014, the project budget is BGN 1 071 158,92. The State Agency for Child Protection and the Social Assistance Agency are partners of the the specific beneficiary MH. The project receives support from NGO “Hope and Homes for Children” and UNICEF. The overall objective is preparation for restructuring of the Homes for Medical and Social Services for Children (HMSCC) aged 0 – 3 by targeted preparatory work in 8 pilot regions: Gabrovo, Montana, Pazardzhik, Pernik, Plovdiv, Sofia, Ruse, Targovishte, applying an analytical approach and synergic intervention with other institutions responsible for the process. The target group includes children aged 0 – 3, placed in the selected HMSCC, and their families; specialised staff involved in childcare at the pilot HMSCC and staff to be employed for provision of the new services; children in the community aged 0 – 3 at risk of abandonment and their families, including relatives or close friends. In the period 01.07.2013 – 30.06.2014, the efforts were focused mainly on intensive and in-depth works with the main target groups and on creating conditions for real transfer of children from HMSCC and their socialisation in a family and close to family environment.

1. Reducing placements in institutions

Only 36 children (including 26 with disabilities) were placed in the 8 pilot Homes for Medical and Social Care for Children over the review period. 35 of them are from the target group. By way of comparison, 88 children were placed in the previous review period, which means that placements have been halved. Placement of healthy babies has been minimised.

Montana is a top performer – over a period of one year, no placements of children aged 0 – 3 in institutions was allowed. Placements are successfully reduced also in Gabrovo District – only 1 child with disability was placed in HMSCC Gabrovo. Placements continue in the other pilot regions, as well as in the HMSCC which are not covered by the project.

There is a need to enhance the efforts for reducing placements in specialised institutions for children aged 0 – 3, in particular in Sofia District. It is essential that the good practices of  Montana and Gabrovo districts are applied in all districts. In that light, in January 2014 MH organised in cooperation with UNICEF a meeting on “Good practices of provision of innovative services for prevention of the abandonment of babies and small children”. Presented were all practices in the 8 pilot districts.

In this review period, the maternity ward (MW) is again the main gate to HMSCC for the better part of the children in the target group. In that light, MH continued to provide, through its regional structures – RHI, continuous methodological support for the actions of medical workers at MW level for prevention of the abandonment of newborns. The efforts of the RHI in the pilot HMSCC are focused on improving the health culture of parents, in particular in the high risk communities, for example: sexual and reproductive health, family planning and counselling, food, hygiene, protecting children in early age from illnesses, getting knowledge on how to protect the child from accidents, violence, etc.

Placement is reduced through synergy and close partnership with the structures of SAA and MH, with local municipalities and NGOs – mainly “Hope and Homes for Children” which support the process in all pilot regions. The good inter-institutional partnerships and networks established for the implementation of the overall deinstitutionalisation process can be highlighted as a major achievement.

2. Transfer of children

Total 75 children were transferred from the 8 pilot HMSCC in the period 01.07.2013 – 30.06.2014. The number of children transferred has dropped dramatically compared to the previous review period when 326 children were taken out. The reason is that 111 children (including only 45 from the target group aged up to 3) remained in the 8 pilot HMSCC at  30.06.2013. In 6 of the pilot homes: HMSCC – Targovishte, HMSCC – Ruse, HMSCC – Sofia,  HMSCC – Pazardzhik, HMSCC – Montana and HMSCC – Pernik all children who were planned to be transferred to family environment were taken out and in the homes remained only children for whom placement in the specialised residential service for children with disabilities and in FTPC for children in the target group aged 3+ was planned as a short-term measure.

In the period 01.07.2013 – 30.06.2014, 41 children from the project’s target group were taken out, including 39 to whom family environment was provided. Children are mainly adopted. 19 children, including 7 healthy and 12 with disabilities, are adopted. Children adopted in Bulgaria prevail – 11, including 4 with disabilities and 7 healthy. 8 children are adopted abroad, all of them with disabilities. 15 children are placed in foster families, including 4 healthy and 11 with disabilities. This is a great success for the deinstitutionalisation process, because foster families’ initial fear to accept children with disabilities is obviously overcome, evident from the the results. 3 children, including 2 with disabilities and 1 healthy, are reintegrated in their biological families. 2 healthy children are placed in kinship families. 2 children with disabilities are placed in close to family environment, in a Center for Family Type Accommodation.

The preparation of each child in the target group for transfer to a family or close to family environment is another activity which is essential for the adaptation of the children and for lowering the traumatic experience from the separation and the fear of change.

After the children are taken out of the institution, monitoring is provided of the reintegration of the children placed in foster families or reintegrated in their biological environment. The local coordinators visit the families every month in order to be able to warn in due time of unforeseen difficulties in the reintegration process and provide support, as necessary. 523 visits were made. It was observed that the adaptation of the children in the family environment goes on normally. The children are calm in the new conditions, there is progress in their development.

3. Process communication and promotion

The communication of the deinstitutionalisation process is one of the project objectives essential for creating supporting environment in the community in the pilot regions so that the attention of all stakeholders is focused on the need to replace institutional care for children aged 0 – 3 by care for them in a family environment. In the period 01.07.2013-30.06.2014, the efforts were focused on motivating and engaging stakeholders in the deinstitutionalisation process. In order to focus their attention on the damages which institutionalisation causes to abandoned children, a poster competition was organised under the motto “Love and Family – This Is What Every Child Needs”. 80 students from all pilot districts took part in the competition. 10 students were selected and were awarded prizes in September 2013. According to the regulation, the winning poster is used as a face of the bag produced as part of the Information and Publicity measures. To enhance public sensitivity to the deinstitutionalisation of children, 8 folklore events were organised in the pilot municipalities among compact ethnic groups in the target regions. The purpose of the folklore events was to ensure that the message of the need to raise children in a family environment and of the damages caused by institutionalisation  will reach the key stakeholders and specific groups of people who could be potential actors in the deinstitutionalisation process. Other information and publicity measures were also implemented.

4. Staff training

Provision of training to the staff of the pilot HMSCC is one of the key project activities. The questionnaire survey of the staff of the pilot HMSCC conducted in mid-2012 contributed for identifying the specific topics of the necessary training. The survey showed that in most cases the staff can be a partner in the deinstitutionalisation process and take active part in the provision of alternative forms of community-based care and services after receiving additional training. The training complemented by supervision was conducted entirely with resource from the partner organisation “Hope and Homes for Children” – Bulgaria with which MH has concluded a Memorandum for Support of the Deinstitutionalisation Process and Provision of Expertise. All staff members, including specialised and auxiliary staff, took part in the training, divided into groups. 8 induction and 8 upgrading trainings were conducted in the pilot HMSCC - 408 staff members of HMSCC received training. 8 individual and 33 group staff supervisions were conducted.

5. Other activities in support of the deinstitutionalisation process

The project provides for holding thematic discussions in all pilot regions to present the designed Regional Deinstitutionalisation Plans. 6 of the discussions were held in the preceding review period. The other 2 thematic discussions on “Planning specific services needed for the restructuring of the pilot HMSCC and deinstitutionalisation of the children” were conducted in July 2013 to present the regional plans in the pilot HMSCC – Ruse and HMSCC – Plovdiv. All regional plans are submitted to the District Administrations for aligned with the existing District Strategies for Social Services.

Steps to extend the project’s validity till 25 November 2014 were taken over the review period.

- PROJECT „I Have Family, Too” (Budget Line BG051РО001-5.2.11 – ACCEPT ME)

Project „I Have Family, Too” is implemented within a direct grant award scheme under Human Resources Development Operational Programme. It is implemented by the Social Assistance Agency in partnership with 83 municipalities across the country and has national coverage. Approved project funding – BGN 14 989 455,30 (at a meeting in March, the Monitoring Committee took a decision to allocate additional resource of BGN 3 200 000 to the project “I Have Family, Too”).

Indicative project implementation timeframe: 30 September 2011 – 31 October 2013.

“I Have Family, Too” is a response to the development of foster care as a protection measure. The project is based on the child’s best interest policy which aims at supporting the foster and biological families and creating the best possible conditions for children’s development and realisation of children’s full potential. In the course of more than 2 years the project has been applying a new approach in the provision of voluntary, professional and respite foster care and works towards increased number of foster families caring for children at risk. The foster care for infants and children up to 3 years placed in institutions, as well as for children with disabilities is a priority in the project implementation.

The project provides for increased funding for support of children up to 3 years placed in foster families. To that end, funds equal to 4 times the amount of the guaranteed minimum monthly income, which is BGN 260.00 per month, have been allocated to these children; the support for children aged 3 - 14 is 3.5 times the amount of the guaranteed minimum monthly income or BGN 227 and that for children aged 14 - 18 (the smallest group of children subject to foster care)  is equal to 4 times the amount of the guaranteed minimum monthly income (BGN 260). Professional foster families are also supported in their effort to provide suitable environment to children with risk and challenging behaviour. In addition, training and consultations for the families of close friends and relatives where children have been placed have been organised.

Performance indicators: number of new forms of community-based social services launched by the end of the Operation – at least in 80 municipalities, included in the operation; number of children from specialised institutions and children at risk of abandonment placed in foster families – by the end of the Operation – 600 children; increased number of foster families – at least 500 persons; increased number of children, biological families, candidates and foster families, and families of relatives or close friends using community-based social services – at least 700 children and persons; increased number of providers of community-based social services – 83.

The project implementation indicators have been achieved, some of them – at two and three times the target set. The promotion of foster care in the community is going on as well as the investigation and training of candidates for foster families. 1 797 applications have been filed by candidates for (including 503 applications in the period 01.07.2013 – 30.06.2014). The subsequent work of the Foster Care Teams (FCT) after the foster families are recognised by the Foster Care Commissions at the Regional Directorates of Social Assistance (RDSA) which results in the placement of a child is carried out in a continuous basis. For a period of one year, 537 final reports have been prepared and 482 foster families have been recognised under the project. (Monitoring the placement of children in cooperation with the Child Protection Departments is part of the daily routine of FCTs.) Last but not least, the support of  foster families where children have been placed has serious influence. 559 professional foster families are reported during the period.

Within the project and with the introduction of the new model of provision of the foster care service in the country, the Child Protection Departments continue their work on updating of the assessments of the children fit for placement in foster families. This is part of the child protection policy aimed only and exclusively in the best interest of the child.

At 30.06.2014, 1 439 children were placed in foster families under the project. The breakdown of children by age is the following: 0–3 – 690 children, 3–14 – 724 and 14–18  – 25 children. The decentralisation of the service has contributed to increased prevention of the placement of children in specialised institutions, with 594 children in the community placed in foster families from the project launch to date. Half of the children are newborns and are placed right from the maternity ward. It should be noted that the children in the community, placed in foster families, are able to keep in contact with their biological parents in view of improving their relationship and ensuring successful reintegration. The implementation of the project activities enable children to live in a family environment and to have access to the necessary services according to their needs and the new approach in the care for them. The implementation of the project activities contributes to the successful deinstitutionalisation of children – i.e., owing to the project foster families 563 children were taken out of specialised institutions and 182 children were taken out of residential services within the overall project implementation.

The support to foster families and families of relatives and close friends where children are placed is also an important aspect. The support is complemented by the program “Training of relatives and close friends with whom children are placed pursuant to Article 26 of the Child Protection Act” designed and approved by PIU and more than 100 families have received training and support. The opportunities to exchange experience, discuss problems, difficulties and achievements from daily life in self-support groups have a positive effect on the motivation, attitudes and perceptions of foster families. This contributes to  a safer, caring and secure environment for raising and recovering children in foster care as a temporary protection measure. An important aspect is also the availability of a forum for sharing goods practices  which could have multiplicatory effect.

At 30.06.2014, more than 143 families of relatives or close friends have been trained whereby the indicator’s target has been achieved. Ten external consultants with expertise in psychological work and counselling have consulted and provided support and supervision to the FCT in their work with foster families. This in turn has helped channel a new, modern approach consisting in individual, group supervision and support of foster families. Guiding in this respect are improved quality of care, provision of a service in accordance with the best interest of the child and establishment of a European foster care model adapted to the Bulgarian conditions. Specialised consultations and supervisions of foster families have been conducted by hired external consultants in each one of the partner municipalities.

One of the most important project tasks is the design of a uniform financial standard for the foster care service, developed on the basis of the experienced gained in the project. An analysis of best practices, the funds expended necessary to cover the service provision cost. The draft uniform financial standard was developed by representatives of the academic circles and was approved by a commission set up by PIU.

The draft UFS was presented as a baseline variant to the Interdepartmental Working Group set up by SAA, which includes representatives of  MLSP, SAA, SACP, Ministry of Finance (MF), NGOs and external experts, in view of designing the final variant of the uniform financial standard. The finalised financial standard will provide a basis to amend the legal regulation of the foster care social service and to establish it as an activity delegated by the state which will also help ensure the project’s sustainability.

The promotion of the project and of the foster care service is provided by PIU and the partner municipalities through postings and publications in the website of SAA, regional and municipal websites, national and local printed media, radio and television programs.

At 30 June 2014, the project validity is extended to December 2014 inclusive, in respect of the resources for maintenance of FCTs, foster families and the children. At this stage it is envisaged that after that date the implementation of the project activities should be completed.

- PROJECT BG051PO001-6.2.13 DEVELOPMENT OF A SYSTEM FOR PLANNING AND PROVISION OF SOCIAL SERVICES AT REGIONAL LEVEL

The project supports the reform initiated in the field of social services in Bulgaria, which in the recent years has imposed as a key priority the deinstitutionalisation and change in the management of the existing institutions towards their restructuring and transformation in community-based services.  The main focus is on enhancing the capacity of the project target groups by promoting the good practices in the planning, management and provision of social services and on adopting mechanisms for effective partnership and interaction between the municipal authorities and non-governmental organisations in the provision of social services.

The project was launched on 3.10.2011. The project budget is BGN 5 226 545,95.

The target group covers 3 440 employees of public institutions (SACP, SAA, Agency for People with Disabilities (APD), municipal and district administrations, etc.), involved in the development and implementation of the policy in the filed of social services, social service providers and their staff, social workers operating in the field of social services. The series of trainings which the project offers to this target group seeks to improve the skills and competences of those employees for management, quality control and assigning the social services management; monitoring and performance assessment of the current strategies for social services development; risk assessment, supervision and crisis intervention, as well as quality control of the social services provision.

Over the review period, training was provided to: 28 trainers on management and provision social services and supervision; 652 employees, including 341 on a programme for monitoring and evaluation of the implementation of policies and strategies for development of social services and quality control of the provision of social services and 312 on supervision and crisis interventions. Upcoming is the provision of training to another 528 employees of the local administrations on the organisation and management of social services and provision of quality control therein, as well as to 1 800 representatives of social service providers on the management and quality provision of services as well as on implementation of mechanisms for effective partnership and interaction between municipal authorities and NGOs in the provision of social services.

Another focus of the project is the provision of specialised support and local and regional capacity building capacity for development of social services through planned organisation of 28 district workshops for exchange of good practices and networking of  social service providers and NGOs.

The appointment of 56 district coordinators responsible for the social services has led to the formation of 28 points of service and their activity is focused mainly on building a coordination unit which should contribute to partnership building , support the development and provision of social services and take care of the implementation of the national priorities in the field of social services. Their work will build on and elaborate the model for building a network of social services at the regional level implemented by UNICEF by  providing daily consultations to municipal authorities, social service providers  and other representatives from related sectors on the matters of planning, managing and  restructuring social services in fulfilment of the strategies and plans for their provision at the local level. In August 2013, the district coordinators prepared analytical reports for each one of the 28 districts, based on the monitoring of activities for deinstitutionalisation of children with disabilities and the existing network of supporting services.

The project supports also the deinstitutionalisation of care for elderly people and contributes to clearing the ground for legislative changes in the social sphere and its future improvement, through the two new activities added, scheduled for implementation in 2014 and 2015. The institutional model of care for people with disabilities and elderly people is still prevalent in Bulgaria. At the same time, there is increased need of long-term care for incapacitated elderly people while the capacity of the existing forms and programmes becomes ever scarcer. At this stage, the system of care for people with mental disorders, intellectual disabilities and dementia placed in the specialised institutions cannot meet the needs of the target groups. In that light, the condition of 160 specialised institutions for elderly people with disabilities and elderly people will be analysed. On the basis of the results of the analysis, the institutions that have to be closed immediately will be identified, as well as the institutions which could be closed on a phased basis during the lifespan of the National Strategy for Long-term Care. It will be further established to what extent the operation of the specialised institutions is in compliance with the existing district and municipal strategies for development of social services and the next district strategies for development of social services will be prepared on that basis. Another new activity aims at studying the quality standards of social services applied in the country with a view to informing legislative changes in the social sphere and contributing to its future improvement. Designing indicators for the quality of social services could be a prerequisite for the development of quality monitoring and control systems to be implemented  for the process of transition, as well as for the services resulting from the transition, with clear focus on meeting the needs of users. The social service quality indicators will be applied in the control and monitoring of specialised institutions and community based social services which are activities delegated by the state and will have direct effect on the reform and modernisation of the long-term care system, leading to provision of high quality, diverse and sustainable forms of home-based and community-based social services meeting the complex (health and psychosocial) needs of elderly people and people with chronic diseases and disabilities.

In January 2014, the project validity was extended till 30.04.2015.

- PROJECT BG051PO001-6.2.09 “Capacity building of the Social Assistance Agency to improve the quality and effectiveness of social work” .

Project “Capacity Building of the Social Assistance Agency to improve the quality and effectiveness of social work”  is implemented by the Social Assistance Agency. It was approved pursuant to direct grant award procedure under Priority Axis 6 of Human Resources Development Operational Programme. The project encompasses 28 districts on the territory of the Republic of Bulgaria. Its target group is formed by employees of the Social Assistance Agency. The project was launched in August 2011 and its budget is BGN 9 480 908,34.

In the period 1 July 2013 – 30 June 2014, recruitment for the vacancies in the “Child Protection” (CPD) and “People with Disabilities and Social Services” departments (PDSSD) of the local Social Assistance Directorates continued on a regular basis with a view to supporting their increased activity as a result of the enlarged target group and the related need to review and re-plan the children placed in HCDPC and refer them to the new services.

Public procurement procedure with three separate lots was announced and contracts were awarded for all positions.

The Social Activities and Practices Institute - the procurement procedure participant under Lot 1 “Consultancy service for designing and implementing systems which provide upgrading knowledge and skills tailored to the specific care for individual groups of community-based social service beneficiaries, planning of adequate trainings” – has designed the systems for induction and upgrading training. They provide the basis for delivery of trainings for the departments  CPD and PDSSD.

Another important focus in the review period is the launching of induction and upgrading trainings for the social workers from the CPD and PDSSD. Trainings are provided by Consortium “EMK” with leading partner “E-TOURS” LTD – participant in the procurement procedure under Lot 2 “Training for the staff in the departments “Child Protection” and “People with Disabilities””. Trainings are provided according to a predefined schedule tailored to the travel opportunities and the engagements of trainees. At 30 June 2014, 55 trainings have been provided and 1 945 persons have received training, including 931 from CPD and 1014 from PDSSD.

The following meetings and conferences were held in the review period:

- Four working meetings of the project management team with the directors of the Social Assistance Directorates, aimed at improving the awareness and the coordination of work of appointed social workers and providing feedback on the trainings and the effectiveness of the new staff appointed under the project.

- Kick-off conference in Sofia on 14 and 15 November 2013 and interim conference in Plovdiv on 26 and 27 2014 within the project publicity and information activities.

A highlight in the activities implemented over the period is the budget increase annex to contract signed in April 2014. The funds are earmarked for increase of the basic salary of appointed social workers from BGN 450 to BGN 475. Additional agreements to the employment contracts have been prepared and executed for the purpose.

A public procurement procedure was organised for the supply of office materials. The contract was signed with RONOS OOD and the office materials were delivered to the Social Assistance Directorates across the country and in the Central Office of SAA.

At June 2014, steps have been taken to extend the project validity till March 2015.

- PROJECT BG161PO002-1.9.01-0001 “SUPPORT”

Project “Support” is implemented by the State Agency for Child Protection /SACP/ and is financed from Technical Assistance Operational Programme /TA OP/. It was launched in May 2012 with two main objectives: to improve the capacity of SACP to manage EU-funded projects under operational programmes and to establish a mechanism for coordination and communication between the five Action Plan projects which is operational at all levels, ensures the participation of all stakeholders in the process of deinstitutionalisation and improves the feedback between them. The project budget is BGN 2 545 540, 97.

Over the one-year review period, notable developments are registered in the implementation of the activities the ongoing achievement of the indicators within the project.

Implementation was registered on all of the eight project activities. A new activity concerning the promotion of the deinstitutionalisation process was added in April 2014. The main focus of project work was support for the local administrations, the local communities and the teams of the new social services in the difficult process of transfer and adaptation of the children and youths from the institutions. Change management, looking for flexible decisions during field work in an environment of opposition by the local community, the challenges to the process, identifying the most pressing issues and possible solutions, the management levels on which the decisions depend – such were the focal points of the work carried out by the “Support” Project team. All stakeholders were given the opportunity to take active part in putting forward and discussing challenges and identifying the most workable solutions.

The highly qualified doctors with expertise appointed for the project worked intensively and focused their efforts on the children and youths with very disabilities from the target group of Project “Childhood for All” whose health status needed to be clarified in view of the upcoming transfers to the new residential services. Medical evaluations of 226 children and youths have been prepared over the period.

The role of the local Regional Teams on Deinstitutionalisation /RTD/ for the overall process development and the ongoing implementation of the five Action Plan projects continued to be very important. The teams include one representative each of RDSA, RHI and RIE for each one of the 28 national districts. Over the review period, there has been a good deal of best practices in the work of RTD in respect of the target group of Project “Childhood for All” – the children and youths with disabilities: the support rendered by RTD Burgas in the first for the country transfer of children and youths to the 2 FTPC in Karnobat Municipality; RTD Kardzhali – for the cooperation with the Complex Pedagogical Assessment Team (CPAT) for opening a class (outside the premises) for the children from HMSCC in Residential Auxiliary School “Dr Petar Beron”, Kardzhali; RTD Montana and RTD Kyustendil – for the cooperation in a casework for finding a parent of a child with disability; RTD Plovdiv – for procuring medical examination and IC of children and youths with disabilities; RTD Sofia District – for procuring CPAT for the children and youths from the home in Vidrare and expert decisions of IC; RTD Vratsa – for procuring integrated education in a mainstream school of children and youths from the target group of “Childhood for All”; for establishing cooperation and coordination with NGOs by RTD Lovech, RTD Shumen, RTD Gabrovo, RTD Varna, RTD Dobrich.

Significant is RTDs’ contribution in closing the institutions and in introducing and establishing alternative and innovative community-based services. The workload of the teams is enormous and they demonstrate high responsibility for the process of transfer and adaptation of the children from the specialised institutions in the new centres. At the same time, RTDs are always in support of municipalities in identifying ways to use the buildings of the specialised institutions being closed. The regional team members were the first to put forward problems and propose solutions which is not surprising, given the fact that they know best the local situation and do fieldwork with the service beneficiaries.

In the 8 pilot municipalities where Project “DESTINATION: family” is implemented,  RTDs are involved in monitoring the implementation of the regional plans and coordination mechanisms and participate as mediators in the process of training the staff of the new services. The representatives of RDSA examine the measures for planning the referral of children and youths and monitor the incorporation of the new services in the district strategies for development of social services. RHI representatives provide assistance for the methodological guidance of the new services and work on the prevention of child abandonment at maternity ward level. With regard to the implementation of Project “I Have Family, Too” RTDs are in continuous contact with the CPD and PDSS staff and the local foster care teams with a view to successfully referring and placing the children designated for foster care in recognised foster families which are appropriate for them. Last but not least, RTDs participate in the Units for monitoring and evaluation of the district strategies for development of social services at regional level which contributes also for the implementation of Project “Development of the system for social services planning and provision at the regional level”, their major role consisting in carefully planning the initiation of the necessary supporting services which are to cover the children and youths with disabilities subject of the deinstitutionalisation process.

Activity 7 of Project “Support” concerning the organisation of a series of working meetings and workshops to exchange experience and information has been intensively implemented since the beginning of 2014. The purpose is to bring together representatives of all stakeholders and actors of the DI process and to identify the critical issues to be addressed at the high management and political level. The target group for participation in the working meetings and workshops was expanded as much as possible to include representatives of local municipal and district administrations and a higher number of experts from different communities, with a view to ensuring maximum communication and improving coordination.

Five regional training meetings were held in 2014 for the teams of the new services to which mayors, deputy mayors, municipal administration representatives, project managers under К2, NDU, etc. were invited. The meetings were organised in Karnobat, Veliko Tarnovo, Montana, Ruse and Pazardzhik in cooperation with the District Information Centres and Cedar Foundation on topics related to the management of the FTPC social services – principles and practices. The training meetings showed in actual fact the quick response to needs in a dynamic and changing environment.

# In April 2014 the validity of Project “Support” was extended till 30 June 2015.

- PROJECT „ Development of Transnational Network for Supporting Children and Families and for Deinstitutionalisation of Child Care”

Project „ Development of Transnational Network for Supporting Children and Families  and for Deinstitutionalisation of Child Care” is implemented by the Ministry of Labour and Social Policy in partnership with the State Agency for Child Protection, the Social Assistance Agency and Autonomous Italian Region Sicily (two other autonomous Italian regions – Calabria and Sardinia, and the autonomous Italian province Bolzano). The main project objective is the efficient transnational cooperation, exchange of good practices and promotion of innovative models of public institutions in Bulgaria and Italy in the field of child care policies. The project was launched in February 2013 and will be implemented till January 2015.

The key project activities include: participation in exchange of good practices, study visits and seminars to acquaint Bulgarian representatives with positive experience in the process of deinstitutionalisation and reforms in the system for support for children and families in Italy; collection and analysis of good practices in the field of deinstitutionalization and support of children and families in Bulgaria and Italy, etc. A key project outcome is the establishment of a sustainable model of cooperation between the Bulgarian and the Italian side through a network for exchange of good practices in the field of social services for children.

One introductory conference, three study visits and one thematic workshop have been organised under the project over the review period:

- Study visit in Florence and in Calabria, Italy (1 – 6 December 2013);

- Introductory conference in Sofia and a study visit in Veliko Tarnovo (26-30 May 2014);

- Study visit in Varna / Shumen and a thematic workshop in Varna (18 June 2014 – 20 June 2014).

Social services for children and specialised institutions for children were attended within the visits with a view to presenting the Bulgarian and the Italian experience in the field.

The focus of the visits planned by the Bulgarian side is on presenting the positive experience of Bulgarian municipalities in the deinstitutionalisation process and the reforms of the system for support of children and families at the local level. Besides, the presentation of these good practices will contribute to raising the awareness and improving the quality of the implemented policies for support of children and families.

A survey was conducted among the municipalities in April 2014. It identified 38 good practices in the field of child welfare, deinstitutionalisation and provision of community based services for children and families.

- PROJECT BG051PO001 7.0.02-0003 „Change Management Through Experience and Knowledge”

Project „Change Management Through Experience and Knowledge” is implemented by the State Agency for Child Protection. Partners to the project are Social Inclusion Directorate of MLSP and NI-CO, Northern Ireland. The project budget is BGN 919 698.14, funded at 100% from Human Resources Development Operational Programme. The implementation timeframe is 22.10.2012 – 22.04.2015 (30 months).

The project has been triggered by the development of the deinstitutionalisation process in Bulgaria and the need to build integrated community-based services and to establish good practices of implementation thereof.

Between July 2013 and June 2014, the project was in its preparatory phase and the efforts were focused on setting up the management team and holding the procurement procedures planned, as well as on preparing the activities laid down in the project.

In its active phase the project will create conditions for exchange of theoretical and practical experience between Bulgarian experts from different sectors and their colleagues from Northern Ireland, thereby leading to enhanced administrative capacity of the institutions and improved quality of experts’ work. The two sides will exchange knowledge and experience through an analysis of the child protection system in Great Britain and Northern Ireland and study visits to different services in Belfast. Proposals for changes to the Bulgarian child protection system will be prepared after the visits to Northern Ireland, on the basis of the reports of the seconded individuals.

Innovative is also the preparation of  Strategic Management Plan for the integrated services in Bulgaria which could provide the basis for the future regional planning of social services.

The project provides for the organisation of a number of trainings for experts from different sectors (healthcare, education, social sphere) with a view to improving their collaborative skills.

The project builds on the achievements of Project “Childhood for All” and contributes to improved quality of life of children and youths in Bulgaria. It addresses also the question of partnerships, interdepartmental cooperation and good planning.

The general project objectives include designing tools and know-how for the new service models at local, regional and national level and improving the competence level of the experts in the social sector for the provision of integrated community based services to children and families. The specific objectives include networking and interaction of the social, health and education experts and specialists; creating conditions for the practical application of the new programmes and models of work within the deinstitutionalisation process and the community-based services.

The target group consists of representatives of the State Agency for Child Protection, of other state institutions, including their regional structures – representatives of Regional Directorates for Social Assistance /RDSA/, Social Assistance Directorates /SAD/, regional Inspectorates of Education /RIE/, Regional Health Inspectorates /RHI/ and other specialists working in the field of social services and deinstitutionalisation. The total number of the target group members is up to 350 individuals.

The core project activities were launched with delay due to different technical problems. A new timeframe of activities has been drawn up and the budget has been updated.

Upcoming is the design and approbation of the Strategic Management Plan for the integrated services in Dupnitsa Municipality which will prove the applicability and viability of the plan. In case of positive feedback, proactive steps will be taken to promote and approve the Plan.

Upon completion of Activity 4 “Study Visits to Great Britain”, an analysis with proposals for changes to the Bulgarian child protection system will be prepared on the basis of the delivered expert reports.

- PROJECT BG051РО001-4.1.07 “INCLUSIVE EDUCATION”

Project „Inclusive Education” under HRD OP co-financed by the ESF provides support for the education in a general education environment of one of the most vulnerable groups – children and students with disabilities. By providing inclusive education and establishing the new models laid down in the project, the access to and quality of education will be improved, knowledge and skills will be built depending on the individual needs of every child, thus increasing the chances for successful social inclusion and ultimately supporting deinstitutionalisation process in general. Two of the activities of Project “Inclusive Education” correspond directly with the deinstitutionalisation process  – Activity 6 “Provision of Supporting Environment by Psychologists, Resource Teachers and Other Professionals for Children and Students Deprived of Parental Care and Placed in Residential Facilities Covered by the Process of Deinstitutionalisation” and Activity 4 “Building a New Model of Organisation and Functioning of Residential (Auxiliary) Schools for Children with Intellectual Disabilities”.

This activity aims at providing support for inclusion through the process of education of children and students deprived of parental care and placed in residential facilities covered by the process of deinstitutionalisation. It is planned to have 64 pilot kindergartens and schools located in close vicinity of the newly established residential services – centers for family-type accommodation and protected homes – in order to create supporting environment for 400 children through hiring 192 professionals – psychologists, resource teachers and other professionals with pedagogical functions. Rooms for personality development are also equipped there. This will enable the process of inclusion of children and students by removing the barriers in learning and facilitating their participation in the educational process. The activity will be performed in stages, which are linked to and depend on the construction and equipment of the centers for family-type accommodation and protected homes, where children will be moved.

Activity 6. Supporting environment is built in appropriate pilot kindergartens and comprehensive schools located in close vicinity of the Centers for Family Type Accommodation and Protected Homes and selected by the Regional Inspectorates of Education on the basis of established criteria. The pilots schools and kindergartens shall be confirmed with an order of the Minister of Education and Science.

The following sub-activities are included in the activity: selection and appointment of psychologists, speech therapists, resource teachers by the directors of the pilot kindergartens and schools in the respective pilot municipalities; work by the psychologists appointed in the pilot kindergartens and schools with the public in the respective area on changing the attitudes and preparing for inclusion of the children from the institutions; study and analysis by the appointed specialists of the general extraordinary evaluation of children’s and students’ needs prepared by the Regional Team on Deinstitutionalisation ; evaluation of the educational needs of the children and students previously not covered by the educational institutions, including of those who have reached the age of 16, etc.

The students are included in the respective form of education which is appropriate for them on a proposal by the school team in coordination with the parent / guardian of every child. The proposal is approved by the Pedagogical Council.

The following forms of education are available: daytime, individual, combined. Students can be included in individual or group work. A class of children with multiple disabilities could be formed (4 – 6 children), provided that two or three special educators are appointed and charged to the school budget. The additional support by the three specialists – a resource teacher, a speech therapist and a psychologist – is charged to the project. Support for children whose health does not permit them to go the kindergarten / school can be provided on-site in the FTPC by specialists appointed under the project.

Total 10 pilot comprehensive schools and 1 kindergarten have been approved at 30.06.2014, with 64 children and students included in education, against a plan of up to 64 school and kindergartens with a total of up to 400 children and students aged 3 – 18, who are deprived of parental care and sue residential services. The specialists in this project activity – resource teachers, speech therapists, psychologists, directors are 35 people in total.

Problems in the implementation of Project Activity 6

The activity is implemented on a non-regular  basis. Its realisation is directly dependent on FTPC and Protected Homes being opened. The provision of up-to-date information about the launch of the activity in the built FTPC and the protected homes, about the period of transfer there of the children and students from the homes for children is essential. The absence of such information creates difficulties for the timely organisation which the project management team of the Inclusive Education Project should provide. The lack of an up-to-date list of the children with information about their age, health status, education, latest grade completed, impedes also the timely planning of the educational capacities – separate class for children with multiple disabilities or individual integration of the children in the respective classes.

There is need of information about the children whose health does not permit them to go to the kindergarten / school, in order to plan specialists who will provide support for children’s education on-site in the FTPC. The lack of correspondence between the timeframes for placement and the timeframes under the education laws makes it impossible to present the results of their education for the respective school year and sometimes prevents the successful completion of the school year. This is obviously not in the interest of the children.

Activity 4. The new model of organisation and functioning of the pilot school – IV Auxiliary School “Prof. D. Katsarov” in Sofia, aims, on one part, to provide education in accordance with the modern requirements for the education of children with severe and multiple disabilities, to enable building knowledge and skills tailored to the individual needs of every child and, on the other part, to provide integrated services (art therapy, kinesitherapy, work with the family, special diet, special daily transport), resulting ultimately in excluding the residential aspect from the structure of the school and ensuring provision of education without separation from the family environment.

The necessary materials and equipment have been built in the pilot auxiliary school and 6 specialised rooms have been equipped for work with children with severe mental disabilities and multiple disabilities; 32 specialist have been appointed to work with the children with severe and multiple disabilities, a new curriculum for children with severe and multiple disabilities has been drafted in relation to the new functional model of the school, etc.

Activity 2 “Creating conditions and providing support for the transition from integrated to inclusive education”

# This activity is also innovative in terms of spirit and philosophy because it contributes to shaping a new policy of the comprehensive school which has to take the initiative and the responsibility to manage the implementation of inclusive education. Teams of specialists have been set up in the 84 pilot comprehensive schools (84 psychologists, 181 resource teachers, 65 speech therapists, 3 teachers of children with impaired vision and 10 hearing and speech rehabilitators), 84 resource rooms have been furnished with the necessary machinery and equipment in support of the education of children with special educational needs; methodology for evaluation of the educational needs of children and students and manual for its implementation have been designed. A model of inclusive education of 1 654 students with special educational needs has been built.

# With Order No. РД 09-1277 / 20.08.2014 of the Minister of Education and Science the project implementation term was extended till 31.08.2015.

- PROJECT „Social Inclusion”

The Social Inclusion Project (SIP) is funded by a loan provided by the International Bank for Reconstruction and Development (World Bank) to the amount of EUR 31 391 644 (BGN 61 396 719). The loan agreement with the World Bank was signed in November 2008 but the project implementation actually started in August 2010. The deadline for utilisation of the loan funds is 30 September 2015.

The fundamental nature of SIP are the early childhood development services. To create adequate conditions for their provision, SIP finances construction works, as well as purchase of equipment and furniture required for the provision of the services.

The Social Inclusion Project aims to prevent social exclusion and to reduce child poverty through investments in the early childhood development. By improving children’s preparedness for inclusion in the educational system and by supporting the formation of parenting skills among the vulnerable groups of parents the project aims to limit the intergenerational transmission of poverty.

The main feature of the services provided for by the SIP is that they will be integrated - through a combination of the social, health and educational element - in a service in terms of both the collaboration of the various specialists with the project target groups and the very nature of the services - social, health, services to support pre-school education, etc.

The main services which will be funded under the project include:

1. Integration of children intoe kindergartens and preparatory groups/classes, which includes creation of places in the kindergartens through construction or renovation of kindergartens, full or partial reduction of the kindergarten fee, individual and group work with children and their parents, including with children and parents, who do not belong to vulnerable groups, provision of transport for the purpose of attending the kindergarten, etc.;

2. Screening of training readiness;

3. Readying for equal start at school by establishing summer schools and/or groups before enrolment in the first grade;

4. Health consultation for children and activities on prevention of diseases, including a visit to a dentist for the older children;

5. Nursery fee reduction;

6. Early intervention of the disabilities through training of medical staff and direct work with children with disabilities and their families from childbirth, which includes, in addition to the rehabilitation in the centres specially created under the project, activities on counselling, training and mobile work with the child in his/her home;

7. Individual pedagogical support for children with disabilities to be enrolled in the first grade;

8. Formation and development of parenting skills through group and individual work with parents and future parents;

9. Family counselling and support, which includes work with the parents and children, family planning activities and individual work to solve specific child raising problems;

10. Family centres for children aged  0-3 and 3-7 years, which will enable the children to receive the appropriate care and training in the absence of a kindergarten or a nursery;

11. Carers of young children in the home.

A total of 66 financing agreements (FA) have been signed with the municipalities whose projects will be funded under the SIP and the total value of the projects amounts to BGN 66 735 125.95, including BGN  59 421 716.08 in loan amounts and BGN 7 313 409.87 in municipal co-financing.

At 30.06.2014, a total amount of BGN 38 054 535.60 is utilised under the SIP, including BGN 33 791 488.54 in loan funds (55% of the loan amount) and BGN 4 263 047.06 in municipal co-financing.

In the review period, the main focus was on amending the Loan Agreement with the World Bank which provides the basis for the funding if SIP. On 30.10.2013, the National Assembly ratified the amendment to the Loan Agreement for the Social Inclusion Project. The main elements in the amendment included extension of the loan term from 31.10.2013 till 30.09.2015, i.e. by 23 months, and reducing the value of the loan for the funding of SIP by EUR 8 608 356 (BGN 16 836 481), i.e. the loan amount was reduced from EUR 40 000 000 to EUR 31 391 644.

Mainly construction works and purchase of equipment and furniture are financed under SIP. 87 contracts for construction works worth BG N 35 585 851 have been concluded. 86 of them, worth BGN 35 452 170.84 in total have been completed. The main construction works under SIP have been completed.

In the second half of 2014, the work under SIP was focused mainly on preparing standard tender documents, including detailed terms of reference, for the selection of the specialists who will provide the early childhood development services under the projects of the municipalities. After their completion by the municipalities, MLSP coordinates the draft tender documents and sanctions the start of selection of the staff who will provide the services. It is provided for that during the summer holidays of 2014 the beneficiary municipalities will provide the service “Additional training for equal start at school” (summer schools).

- PROJECT FOR DEINSTITUTIONALISATION OF CHILDREN AGED 3 - 18 PLACED IN HCDPC. Preliminary analysis and forecast.

The analysis is based on information from the annual surveys of the condition of children placed in special institutions conducted by the State Agency for Child Protection:

At 31 December 2013, in the Homes for Children Deprived of Parental Care 1 388 children and 104 youths aged 3 – 18 and left in the home until they complete their education were raised. Compared to 2001, the number of children placed in these homes has decreased by 5 757 people or 80.6% and compared to the previous 2012, the number of children placed in HCDPC has decreased by 504 people or 26.6%.

At year end, 359 children use the social services in these homes with a referral by CPD for weekly or daily care, including 273 children using weekly care and 86 – daily care. The capacity of HCDPC for 2013 is 2 320 places, decreasing by 568 places or almost 20% compared  to the previous year.

At 30 June, there were 50 operational Homes for Children Deprived of Parental Care in the country, in which 1 235 children and 78 youths were placed. Healthy children without disabilities or chronic disease prevail in HCDPC, making up almost 68% of the children placed in these homes. Children with different level of intellectual disabilities make up the highest share in the total number of children with illnesses and/or disabilities – 15% (211 children).

In the current review period, children aged 12 – 17 account again for the highest share – 794 children or 57%. Out of the children placed in institutional care in HCDPC, those aged 8 – 11 are 390 and those aged 4 – 7 are 204. In 2013, 562 children were placed, including 58% first entrants in the system of institutional care for children. In 2013, 900 children left the homes for children deprived of parental care. The highest share is that of the children reintegrated in their biological families (25%) or placed in foster families (25%). In 2013, 82 children from the homes were adopted. Over the year, 52 children placed in HCDPC were placed in families of relatives or close friends. About 6% (50) of the children were transferred to another specialised institution, in most cases homes for children deprived of parental care aged 7 - 18,  or if an illness is established – residential institutions for children and youths with intellectual disabilities.

Over the year, 119 youths left the HCDPC for the reason of having attained majority. In most cases youths go back to their biological families or to families of relatives or close friends. Total 41 youths or 34% of those who left the HCDPC because of having attained majority went back to their biological families, 18 youths live in families of relatives or close friends, 14 youths are taken out in protected homes and 21 – in supervised homes. The directors of the homes report that 25 of the youths who have left over the year live and work on their own.

In the first six months of 2014, 198 children were placed in the homes for children deprived of parental care and 361 left the those institutions.

B. Legislative Changes Securing the Deinstitutionalisation Process

- Legislative changes implemented in the past year

The amendments to the Rules for implementation of the Social Assistance Act (RISAA) of July 2014 which will take effect from 01.01.2015, introduce a differentiated approach in determining the standards for financing from the municipal budgets of the social services Center for Family Type Accommodation, Protected Home and Day Care Centre which are activities delegated by the state. The initiated amendments to IRSAA are aimed at applying a differentiating criterion for the placement of users of different profile and needs characteristics in those social services.

The differentiated increase is aimed at better allocation of funds and at provision of targeted support, taking into account the specifics of the work with certain target groups in the services. In the services where care is provided to people with disabilities the percentage increase is notably higher compared to that for services the users whereof are in a better state of health or without disabilities. This differentiation was taken into account in planning the funds for 2015 for the social services which are activities delegated by the state.

The Transitional and Final Provisions of the Decree of the Council of Ministers amending and supplementing the Rules for implementation of the Family Allowances Act (RIFAA) introduce a material amendment in § 1а of the Additional Provision of the RISSA The amendment achieves equality of the children placed in residential care when going to school and guarantees this right regardless of any disability and in accordance with the principle of non-discrimination, in view of exhaustive coverage of the target group. Thus all students placed in specialised institutions for children, as well as in resident-type social services such as transitional housing, crisis centre and center for family-type accommodation, receive, starting from 01.01.2014, monthly allowance for pocket expenses the amount of which was also increased. These funds are allocated annually with a Decision of the Council of Ministers for the respective year and are paid through the budgets of the municipalities where the respective services are located.

In 2013, the one-time targeted benefit for students enrolled in first grade of a state or municipal school in the 2013/2014 school year was increased from BGN 150 to BGN 250.

An increase of the allocations for payment of all family benefits under the Family Allowances Act by BGN 69 497 440 was planned in the 2014 budget. The total allocations for benefits under FAA amount to BGN 556 397 462. The highest increase, at BGN 49 200 000, is allocated to the resources for monthly allowances for a child until completion of secondary education. The total amount of the resources for this type of benefit is now BGN 399 558 000.

The 2014 State Budget Act introduces in the Family Child benefits Act differentiated amounts of the monthly allowances for a child  – BGN 35 for first child, BGN 50 for second child, and BGN 35 each for third and any subsequent child. Benefits for twins and children with permanent disabilities are also increased, from BGN 52,50 to BGN 75 and form BGN 70 to BGN 100, accordingly.

With a view to achieving more adequate support for the families raising a child with permanent disabilities, the monthly allowance for children with permanent disabilities was increased from BGN 217 to BGN 240, starting from the beginning of 2014. With the raise of the minimum salary starting from the beginning of 2014 (from BGN 310 to BGN 340) the monthly remuneration of professional foster families was also increased.

- Major challenges and recommendations

# The implementation of the deinstitutionalisation of child care has outlined a permanent downward trend in the number and capacity of specialised institutions and an upward trend in the number of community-based social services for children. In that light, it is of fundamental importance to reallocate the funds released as a result of the reduced capacity or closure of specialised institutions for children to community-based social services which are an alternative of institutional care. In 2014 and 2015 the project financing of a number of services will be completed and, with that in view, the necessary steps for planning resources for the provision of these services as activities delegated by the state have been taken, With a view to ensuring sustainability of the services initiated within the deinstitutionalisation of child care, in 2015 some of the new social services under the project „Childhood for All” and the operation “Life in the Community” will  be financed as state delegated activities.

# In order to outline the major challenges and recommendations concerning the legislative changes over the review period, account has to be taken of the coming into force and the practical application of amendments. Thus, the amendment to RISAA, concerning the implementation of a differentiated approach in determining the financial standards for social services will take effect from 01.01.2015 and it is not possible yet to make conclusion about its future application. As regards the amendments to FAA, which took effect from 01.01.2014, and the implementation of the 2014 State Budget Act in relation to the differentiated monthly benefits for children, recommendations in the context of future challenges could be made not until the Social Assistance Agency makes a quantitative analysis of the efficiency of the measures taken and the financial execution for the year is closed, as well as after the 2014 policy implementation report is prepared.

# The amendment to IRSAA concerning the provision of monthly benefits for pocket expenses of students placed in specialised institutions for children and in resident-type social services took effect from 01.01.2014. These funds will be paid through delegated budgets to the municipalities which should report on the effect.

C. Financial means and resources in the deinstitutionalisation process

- Size of the Funding Provided by the State Budget for State Delegated Services

The social services which are activities delegated by the state and support the overall deinstitutionalisation process are financed from the state budget for the respective year with a global subsidy determined on the basis of financial standards and physical indicators for the respective activity approved by the Council of Ministers.

The amount given for the funds for state delegated activities (thousand BGN) for 2014 corresponds to the adjusted budget with compensated changes and is as follows:

1. Specialised institutions for provision of social services for children:

- HCPD – 579,6;

- RICID – 9902,9;

- HCDPC age 3 – 7 – 2087,9;

- HCDPC 1 – 13 grade inclusive – 11814,6.

2. Community-based social services (for children and adults):

- Day Care Centre for Children and/or Adults with Disabilities – 24163,4;

- Week care Centre for Children with Disabilities – 968,5;

- Centre for Social Rehabilitation and Integration – 9695,4;

- Community Support Centre – 2654,7;

- Mother and Baby Unit – 623,9;

- Shelter – 328,9;

- Centre for Working with Children in the Street– 1832,2;

- Crisis Centre – 1784,2;

- CFTA for children – 12478,6;

- Transitional Housing – 1684,8.

3. Monthly benefit per student in HCDPC 1 – 12 grade – 643,1;

4. Monthly benefit per student in Crisis Centre, Cenre for Family Type Accommodation, Transitional Housing, Home for Children with Physical Disabilities and Homes for Children with Intellectual Disabilities – 755,2.

The implementation of Programme “Child protection by transition from institutional care to alternative care in family environment” has been regulated in the Child Protection Act and the Rules for its Implementation and is implemented by SAA in accordance with the principles of protection – raising children in family environment, including by providing financial support to families. The programme provides for replacement of institutional child care by community-based family or close to family environment which is not limited only to the transfer of children from the institutions but is also aimed at preventing the placement of children in institutions and at creating new opportunities for community based support for children and families.

The programme aims at providing financial support to families for raising children in family environment. The financial support is an element of the work on prevention of abandonment, reintegration, in the event of placement of children in families of relative or close friends and in foster families.

BGN 10 400 000 are confirmed in the 2014 budget for provision of financial support for raising a child in family environment pursuant to the Rules for Implementation of the Child Protection Act. Including BGN 1 500 000 earmarked for wages and social security contributions of professional parents.

The assistance paid under the Child Protection Act in the first half of 2014 amounts to BGN 5 643 040 for monthly average number of 835 cases of and BGN 2 669 863 were paid for wages and social security contributions of monthly average number of 835 professional foster parents.

By way of comparison, the funds reported for the first six months of 2013 amount to BGN 5 465 095 for monthly average number of 5 523 cases and BGN 2 136 239 were paid for wages and social security contributions for monthly average number of 775 professional foster parents.

The comparative analysis of the two review periods shows that in the first six months of 2014 the monthly average number of cases of provided financial support for raising a child in family environment pursuant to the Rules for Implementation of the Child Protection Act increased by 110 or approximately 2% compared to 2013.

In view of improving the funding system and achieving higher efficiency and effectiveness of social services, it is necessary to make changes in the mechanism of delivery of social services. In that light, it has to be pointed out again that an Interinstitutional Working Group with wide participation of representatives of all stakeholders was set up with an order of the Minister of Labour and Social Policy of 02.04.2014 and tasked to draft the Social Services Act.

- Project Funding

Projects in the Action Plan of National Strategy “Vision for Deinstitutionalisation of Children in Bulgaria”

| Project, grant scheme | Programme funding for the programming period 2007 – 2013 (EU + NF) |  |  | Contracted funding 2007 – 2013 (EU + NF)* |  |  |  |  |  | Payments (EU + NF) |  |  |  | Verified Costs (EU + NF) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ESF | ERDF | EAFRD | ESF |  | ERDF |  |  | EAFRD | ESF | ERDF |  | EAFRD | ESF | ERDF |  | EAFRD |
| Project 1 “Deinstitutionalisation of children placed in homes for children with disabilities” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| “Don’t Leave a Child Out”, Component 1 – project „Childhood for All” | 5 000 000 |  |  | 4 960 400,17 |  |  |  |  |  | 2 633 478,14 |  |  |  | 2 403 014,01 | 5 000 000 |  |  |
| Infrastructural Component – building residential and supporting services |  | 106 976 440 | 17 015 721 |  | 98 176 775 |  |  | 15 27 6 806 ,53 |  |  | 68 355 395 |  | 15 276 806, 53 |  | 57 420 731 |  |  |
| “Don’t Leave a Child Out“, Component 2 – Opening new community-based services | 30 398 658, 38 |  |  | 23 307 764, 33 |  |  |  |  |  | 3 433 896,52 |  |  |  | 922 806,04 |  |  |  |
| Total Project 1 | 159 390 819, 30 |  |  | 141 721 745,9 |  |  |  |  |  | 89 699 576,19 |  |  |  | 65 746 551, 05 |  |  |  |
| Project 2 “Deinstitutionalisation of children placed in homes for medical and social care for children” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| “Chance for Happy Future“ – Component 1 Project „DESTINATION: family“ | 2 000 000 |  |  | 1 972 503,62 |  |  |  |  |  | 551 842,39 |  |  |  | 211 163,07 |  |  |  |
| Infrastructural Component for Restructuring the HMSCCs |  | 9 970 733,81 |  |  |  | 9 970 733,81 |  |  |  |  | 4 515 679,51 |  |  |  | 1 589 622,21 |  |  |
| “Chance for Happy Future” – Component 2 | 4 690 745,14 |  |  | 4 690 745,14 |  |  |  |  |  | 223 111,36 |  |  |  |  |  |  |  |
| Total Project 2 | 16 661 478, 95 |  |  | 16 633 982,57 |  |  |  |  |  | 5 290 633,26 |  |  |  | 1 800 785,28 |  |  |  |
| Project 3 “Deinstitutionalisation of children from homes for children deprived of parental care and of young adults with physical, intellectual and mental disabilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1 – ESF funded | 15 275 207 |  |  | 350 575,19 |  |  |  |  |  | 46 129,28 |  |  |  | 46 129,28 |  |  |  |
| Component 2 – ESF funded | 14 000 000 |  |  | 3 401 231,48 |  |  |  |  |  | 598 326,03 |  |  |  | 587 934,48 |  |  |  |
| Total Project 3 | 29 275 207 |  |  | 3 751 806,67 |  |  |  |  |  | 644 455,31 |  |  |  | 634 063,76 |  |  |  |
| Project 4 “Development of foster care” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project “Have Family, Too“ | 15 000 000 |  |  | 14 989 455,30 |  |  |  |  |  | 1 1758 114 |  |  |  | 10 682 880 |  |  |  |
| Total Project 4 |  |  |  | 14 989 455,30 |  |  |  |  |  | 1 1758 114 |  |  |  | 10 682 880 |  |  |  |
| Project 5 “Capacity Building of the Social Assistance Agency to Improve the Quality and Effectiveness of Social Work” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity Building of the Social Assistance Agency to Improve the Quality and Effectiveness of Social Work | 9 381 468,16 |  |  | 9 408 908,34 |  |  |  |  |  | 7 217 600,78 |  |  |  | 6 904 155,30 |  |  |  |
| Total Project 5 |  |  |  | 9 408 908,34 |  |  |  |  |  | 7 217 600,78 |  |  |  | 6 904 155,30 |  |  |  |
| Project 6 “Development of the Service Provision System at Regional Level” |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| “Development of a System to Plan the Provision of Services at Regional Level” | 4 626 545, 95 |  |  | 2 327 493,98 |  |  |  |  |  | 2 327 493,98 |  |  |  | 2 214 776,74 |  |  |  |
| Total Project 6 |  |  |  | 5 226 545,95 |  |  |  |  |  | 2 327 493,98 |  |  |  | 2 214 776,74 |  |  |  |

Projects created in support of the deinstitutionalisation process

| Project, grant scheme | Programme funding for the programming period 2007 – 2013 (EU + NF) |  |  | Contracted funding 2007 – 2013 (EU + NF)* |  |  | Payments (EU + NF) |  |  | Verified Costs (EU + NF) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ESF | ERDF | EAFRD | ESF | ERDF | EAFRD | ESF | ERDF | EAFRD | ESF | ERDF |  | EAFRD |
| Project “Support” |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project “Support” |  |  |  |  | 2 545 540, 97 |  |  | 901 419, 72 |  |  |  | 746 081, 98 |  |
| Project “Transnational Network for Child and Family Support and Deinstitutionalisation of Child Care” |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project “Development of Transnational Network for Supporting Children and and Families and for Deinstitutionalisation of Child Care” |  |  |  | 920 863,55 |  |  |  |  |  |  |  |  |  |
| Project “Change management through experience and knowledge” |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project “Change management through experience and knowledge” |  |  |  | 919 698, 14 |  |  | 100 684, 44 |  |  |  |  |  |  |
| Project “Inclusive Education” |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project “Inclusive Education” – Activity 6 Activity 4 |  |  |  |  |  |  | 220 740. 86 626 668 |  |  | 180 042. 11 626 668 |  |  |  |
| Social Inclusion Project financed by the World Bank |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Inclusion Project * |  |  |  | 61 396 719 |  |  | 38 054 535, 60 |  |  |  |  |  |  |

* Contracted funding in the project budgets is given at 30 June 2014

- Funding under RD OP

# Grant Scheme BG161РО001/1.1-12/2011 “Support for deinstitutionalisation of social institutions for services provided to children at risk” implemented under Regional Development OP 2007-2013 with total budget of BGN 107 million.

# Objectives:

- To improve the social infrastructure of urban areas where community based services are provided to children and youths placed in RICIDs and HCPDs, and to children with disabilities over 3 years of age placed in HMSCCs;

- To ensure social inclusion and equal access of children and youth with disabilities placed in RICIDs and HCPDs and of children with disabilities over 3 years of age placed in HMSCCs.

- To support the provision of infrastructure for community-based services offered to children and adults with disabilities according to the National Residential Services Map.

# Interventions include:

# - 	Construction of Centres for Family Type Accommodation and their surrounding space;

# - 	Construction, repair, reconstruction, renovation of buildings for Protected Homes (vertical and horizontal house extensions, reconstruction and restructuring of the environment), including the surrounding areas;

# -	Implementation of energy efficiency measures in the above mentioned buildings/premises including heating insulation, replacement of windows, local systems and/or connections to heating and gas supply systems;

# - 	Implementation of systems/equipment to use renewable energy sources to meet the energy needs of the building subject to intervention, where no income (profits) is generated for the beneficiary in the process of their exploitation;

# - 	Supply of appropriate equipment and furnishing for the above buildings/premises related to the provision of residential and social services.

# Specific beneficiaries of the project are 62 municipalities in urban agglomerations covered by the National Residential Services Map. Programme funding at the beginning of the programming period amounts to BGN 106 976 440.

# TOTAL 61 contracts are concluded to date for total grant amount of BGN 98 176 774,68 under which 132 FTPC and 26 protected homes will be built.

# The implementation of 30 contracts has been completed at 30 June 2014 and the Managing Authority of RD OP has approved the request for payment of the balance. Under the grant scheme, 48 CFTA have been built, 9 protected homes were built, furnished and equipped and 4 protected homes were repaired and equipped.

- Funding under the Rural Development Programme (RDP)

Measure 321 “Basic Services for the Population in and Economy of the Rural Regions” under the Rural Development Programme supports investments in infrastructure and equipment which serves the development of services for the population and economy in the rural areas, including the construction or modernisation of centres for social services for children and youths laid down in the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” and its Action Plan, including specialised transport. Rural Development Programme 2007 – 2013 provides earmarked funding for the construction of 16 family-type placement centres, 9 protected homes, 1 Day Care centre for children with disabilities and 8 centres for social rehabilitation and integration in 19 municipalities covered by the National Services Map.

Activities implemented to date: In the period 28 November 2011 – 29 June 2012 a call for proposals was announced for investments to build or improve social service centres for children and youths, provided for in the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” and the Action Plan for its implementation, including special transport.

In order to ensure that the funds from the European Agricultural Fund for Rural Development and the national budget will be used to build infrastructure which creates supporting, near family environment for the children and youths with disabilities, the municipalities coordinated with SACP the terms of reference for design, engineering design or detailed design and technical specifications for furniture and equipment in terms of building functionality, accessible architectural space, location.

In the period announced for acceptance of proposals for support, all of the 19 municipalities covered by the National Services Map submitted their proposals.

Grant contracts were signed with all of the 19 municipalities in the period 3 – 11 October 2012. Detailed information on subsidies and investments is presented in Table No. 1.

Table No. 1 Information on Subsidies and Investments by Municipality:

| Grant beneficiary | Subsidy (BGN): | Contract signature date: | The project will construct or improve: |
| --- | --- | --- | --- |
| 1. Strazhitsa Municipality | 333 414,00 | 3 October 2012 | 1 PH |
| 2. Pordim Municipality | 1 961 910,00 | 3 October 2012 | 2 FTPC, 1 PH, 1 CSRI |
| 3. Dolni Chiflik Municipality | 646 734,00 | 3 October 2012 | 1 FTPC |
| 4. Levski Municipality | 776 816,00 | 9 October 2012 | 1 FTPC, 1 CSRI |
| 5. Berkovitsa Municipality | 370 816,00 | 3 October 2012 | 1 FTPC |
| 6. Kula Municipality | 340 304,00 | 3 October 2012 | 1 PH |
| 7. Elena Municipality | 333 958,00 | 3 October 2012 | 1 PH |
| 8. Elhovo Municipality | 675 166,00 | 3 October 2012 | 1 FTPC |
| 9. Pavlikeni Municipality | 1 548 414,00 | 3 October 2012 | 2 FTPC, 1 PH, 1 CSRI |
| 10. Biala Municipality | 578 958,00 | 3 October 2012 | 1 PH |
| 11. Lukovit Municipality | 1 599 440,00 | 3 October 2012 | 2 FTPC, 1 CSRI |
| 12. Svilengrad Municipality | 344 676,00 | 3 October 2012 | 1 PH |
| 13. Momchilgrad Municipality | 675 688,00 | 3 October 2012 | 1 FTPC |
| 14. Krushari Municipality | 316 008,00 | 3 October 2012 | 1 PH |
| 15. Kotel Municipality | 1 001 924,00 | 3 October 2012 | 1 FTPC, 1 CSRI |
| 16. Belogradchik Municipality | 666 634,00 | 3 October 2012 | 1 FTPC |
| 17. Tutrakan Municipality | 829 650,00 | 3 October 2012 | 1 FTPC, 1 CSRI |
| 18. Pravets Municipality | 1 118 048,00 | 11 October 2012 | 1 FTPC, 1 PH, 1 CSRI |
| 19. Isperih Municipality | 909 716,00 | 3 October 2012 | 1 FTPC, 1 DCC |

At the end of 2012, the municipalities which signed contract with State Fund Agriculture – Paying Agency received advance payments in an amount of 50% of the approved grant for the project.

- Upcoming activities: Currently municipalities hold procurement procedures and have to complete their project by 15 July 2015 at the latest.

- During the project implementation period the team worked on organising and holding procurement procedures – open procedures pursuant to PPA which are now under implementation. The information is provided in Table No. 2:

Table No. 2 Information on the stage of the procurement procedure, by municipality:

| Grant beneficiary | Stage of the procurement procedures organised by the municipalities |
| --- | --- |
| 1. Strazhitsa Municipality | Coordinated general stage. Coordinated construction works. |
| 2. Pordim Municipality | Coordinated general stage. Coordinated construction works. |
| 3. Dolni Chiflik Municipality | Coordinated general stage. Coordinated construction works. |
| 4. Levski Municipality | Coordinated general stage. Coordinated construction works. |
| 5. Berkovitsa Municipality | Coordinated general stage. Coordinated construction works. |
| 6. Kula Municipality | Coordinated general stage. Coordinated construction works. |
| 7. Elena Municipality | Coordinated general stage. Coordinated construction works. |
| 8. Elhovo Municipality | Coordinated general stage. Coordinated construction works. |
| 9. Pavlikeni Municipality | Coordinated general stage. Coordinated construction works. |
| 10. Biala Municipality | Coordinated general stage. Coordinated construction works. |
| 11. Lukovit Municipality | Coordinated general stage. Coordinated construction works. |
| 12. Svilengrad Municipality | Coordinated general stage. Coordinated construction works. |
| 13. Momchilgrad Municipality | Coordinated general stage. Coordinated construction works. |
| 14. Krushari Municipality | Coordinated general stage. Coordinated construction works. |
| 15. Kotel Municipality | Coordinated general stage. Coordinated construction works. |
| 16. Belogradchik Municipality | Coordinated general stage. Coordinated construction works. |
| 17. Tutrakan Municipality | Coordinated general stage. Coordinated construction works. |
| 18. Pravets Municipality | Coordinated general stage. Coordinated construction works. |
| 19. Isperih Municipality | Coordinated general stage. Coordinated construction works. |

Table No. 3 Information on submitted applications for payment of the balance, by municipality:

| Grant beneficiary | Submitted application for payment of the balance (BGN): | Constructed or improved under the project: |
| --- | --- | --- |
| 1. Lukovit Municipality | 1 549 277.60 | 2 FTPC, 1 CSRI |
| 2. Svilengrad Municipality | 295 819.44 | 1 PH |
| 3. Momchilgrad Municipality | 663 717.04 | 1 FTPC |

Table No. 4 Information on the final subsidy paid, by municipality:

| Grant beneficiary | Approved subsidy (BGN): | Final subsidy paid (BGN): | Constructed or improved under the project: |
| --- | --- | --- | --- |
| 1. Lukovit Municipality | 1 599 440,00 | 1 549 277.60 | 2 FTPC, 1 CSRI |
| 2. Svilengrad Municipality | 344 676,00 | 295 819.44 | 1 PH |

“Financed projects” under Project 1 “Deinstitutionalisation of children placed in homes for children with disabilities”, line “Infrastructure component for building residential and supporting services“ – the following information was provided:

1. Programmed funds for the 2007 – 2013 programming period (EU + NF) – EUR 8 700 000.

2. Contracting 2007 – 2013 (EU + NF) – EUR 7 810 907,15

3. Payments (EU + NF) – EUR 943 383,14

4. Verifications (EU + NF) – EUR 943 383,14

5. Payments (EU + NF) in the period 1 July 2013 – 30 June 2014 – EUR 943 383,14

# 6. Verifications (EU + NF) in the period 1 July 2013 –30 June 2014 – EUR 943 383,14

D. Additional resources in support of the deinstitutionalisation process

- Licensed social service providers

Pursuant to Article 43b (1) of the CPA, the Chairperson of SACP is empowered to issue to persons in the meaning of Article 18 (1) 3 or 4 of SAA licenses for the provision of social services for children, whereby ex-ante control on the provision of social services for children is exercised.

At 30.06.2014, the Chairperson of the State Agency for Child Protection has issued 258 licenses to 211 companies and NGOs for the provision of 340 social services for children. In the period 01.07.2013 –30.06.2014, the Chairperson of SACP issued 89 licences for 118 social services for children.

The licensing regime introduced as a condition for the initiation of social services for children and families aims first to introduce ex-ante control for compliance of the services with the criteria and standards of social services for children and the designed and approved methodological guidance for provision of social services. Second, the licensing procedure enables SACP to maintain at national level a register of the providers of social services fro children and families.

- Services contracted to different providers

The Social Assistance Act and the Rules for its Implementation allows for contracting out social services – delegated state function – to external providers. Operational data on provision of social services to children – delegated state function – collected and monitored by the Child Protection Departments with the Social Assistance Agency show that as of July 2014 municipalities have contracted out 104 social services to external providers (most often to NGOs).

Contracted out Services: Community Support Centre, Mother and Baby Unit, Centre for Family Type Accommodation, Centre for Working with Children in the Street, Shelter for Neglected Children, Crisis Centre, Centre for Social Rehabilitation and Integration of Children, Day Care Centre for Children with Disabilities. They are managed by 54 NGOs.

Community Support Centres (CSC)

- CSC – Gotse Delchev – Symbol of Love Foundation - Day Care Centre for Children with Disabilities;

- CSC – Velingrad – Regional Centre for Social Activities and Practices;

- CSC – Pazardzhik – Consortium “Alliance for Social Development” – partners “Protection” and Association “Partners DIT”;

- CSC – Panagyurishte – Social Practices in the Community Foundation;

- CSC – Razgrad – Janeta Association

- CSC – Sofia – Animus Foundation Association;

- CSC – Targovishte – International Social Service Bulgaria Foundation;

- CSC  – Novi Pazar – SOS! Women and Children Victims of Violence Association;

- CSC  – Stara Zagora – Samaritans Association;

- CSC  – Shumen  – Social Activities and Practices Institute;

- CSC  – Veliko Tarnovo – International Social Services – Bulgaria Foundation;

- CSC  – Dryanovo – Development Community Centre;

- CSC  – Sevlievo – International Social Service Bulgaria;

- CSC  – Dobrich – Bulgarian Red Cross Association;

- CSC  – Russe – Equilibrium NGO;

- CSC  – Sofia – Social Activities and Practices Institute;

- CSC  – Sofia – For Our Children Foundation;

- CSC  – Ihtiman – Sonic Start, Ltd.;

- CSC  – Parvomay – Sonic Start, Ltd.;

- CSC  – Dupnitsa – Sonic Start, Ltd.;

- CSC  – Karlovo – Sonic Start, Ltd.;

- CSC  – Plovdiv – For Our Children Foundation;

- CSC  – Plovdiv – Regional Development Foundation “Roma” – Plovdiv;

- CSC  – Smolyan – International Social Service Bulgaria Foundation;

- CSC  – Gabrovo – Imka Youth Christian Association - Gabrovo;

- CSC  – Varna – Vladislavovo Foundation;

- CSC  – Silistra – Ekaterina Karavelova Women’ Association;

- CSC  – Vidin – Social Activities and Practices Institute

- CSC – Krichim /Sonic Start/;

- CSC – Kazanlak /Future for the Children with Disabilities Association – Kazanlak (LO) and Samaritans Association – Stara Zagora (PO)/;

- CSC – Ruse /RCO Caritas/;

- CSC – Balchik /Sonic Start/;

- CSC – Levski /Sonic Start/;

- CSC – Dragoman /Sonic Start/;

- CSC – Kavarna /Sonic Start/.

Mother and Baby Unit (MBU)

- MBU – Pazardzhik – Consortium “Alliance for Social Development” – partners “Protection” and Association “Partners DIT;

- MBU – Sofia – Animus Foundation Association;

- MBU – Stara Zagora – Samaritans Association;

- MBU – Shumen  – Social Activities and Practices Institute;

- MBU – Targovishte – MSS Bulgaria Foundation

Shelter for Homeless Children (SHC):

- SHC – Russe – Bulgarian Red Cross District Council – Russe;

- SHC – Varna – Gavrosh Association

Centre for Working with Children in the Street (CWCS)

- CWCS – Varna – Gavrosh Association;

- CWCS – Russe – Bulgarian Red Cross District Council – Ruse;

- CWCS – Shumen – Social Activities and Practices Institute;

- CWCS – Russe – Equilibrium NGO;

- CWCS – Suvorovo – Social Development and Integration Association;

- CWCS – Sofia – Children and Youth Association;

- CWCS – Pazardzhik – Alliance for Social Development Consortium – Pazardzhik.

- CWCS –Vidin – Free Youth Centre;

- CWCS – Vidin – Social Activities and Practices Institute.

Centre for Family Type Accommodation (CFTA):

- CFTA  – Bata village, Pomorie Municipality, Burgas District – Social Security Municipal Company – Pomorie;

- CFTA  – Burgas – Roncalli Child Centre Association;

- CFTA  – Veliko Tarnovo – SOS Kinderdorf – Bulgaria;

- CFTA  – Velingrad – Community Social Practices Foundation;

- CFTA  – Pazardzhik – Bulgarian Red Cross Association Pazardzhik;

- CFTA  – Plovdiv – For Our Children Foundation;

- CFTA  – Russe– Equilibrium NGO;

- CFTA  – Russe – Child and Space Association;

- CFTA  – Sofia – Child and Space Association;

- CFTA  – Kyustendil – Cedar Foundation;

- CFTA  – Smolyan – International Social Service Bulgaria Foundation;

- CFTA  – Kichevo village, Aksakovo Municipality – St. Andrew Social Association, Bulgarian-German Non-Profit Association

- CFTA  – Gabrovo – Foundation for Social Change and Inclusion;

- CFTA  – Dalbok Dol village, Troyan Municipality, Lovech District – Child and Space Association;

- CFTA  – Lesichevo village, Lesichevo Municipality, Pazardzhik District – Julevia Dom Foundation for Social Services;

- CFTA  – Karlovo, Plovdiv – Sonic Start Ltd

Crisis Centre (CC)

- CC – Silistra – Ekaterina Karavelova Women’ Association;

- CC – Pleven – Opened Doors Centre;

- CC – Burgas – Demetra Association;

- CC – Peshtera – Crime Prevention Fund – IGA;

- CC – Sofia – Animus Foundation

- CC – Sredets – Demetra Association.

Centre for Social Rehabilitation and Integration (CSRI)

- CSRIC – Varna – Karin Dom Foundation;

- CSRIC – Pazardzhik – Protection Association;

- CSRIC – Stara Zagora –Alternative 55 Association;

- CSRIC – Varna – Joy for Our Children Foundation;

- CSRIC – Varna – Euro Integration Association;

- CSRIC – Varna – Centre for Social Rehabilitation and Social Contacts for Children and Adults with Impaired Vision;

- CSRIC – Kyustendil – Institute for Social Policies and Social Work;

- CSRIC – Plovdiv – Crime Prevention Fund – IGA;

- CSRIC – Plovdiv – Different but Equal Association;

- CSRIC – Veliko Tarnovo – International Social Service Bulgaria Foundation;

- CSRIC – Russe – Child and Space Association;

- CSRIC – Targovishte – International Social Service Bulgaria Foundation.

- CSRI – Kresna Municipality – New Choice Organisation;

- CSRI – Shumen – Roma Foundation “Iskra”.

Day Care centre for children with disabilities (DCCCD),

Day Care centre for children and adults with disabilities (DCCCAD)

- DCCCD – Gotse Delchev – Symbol of Love Foundation – Day Care Centre for Children with Disabilities;

- DCCCD – Razlog – Chance Association;

- DCCCD – Vidin – The Unique Children of Vidin Foundation;

- DCCCD – Vidin – The Unique Children of Vidin Foundation;

- DCCCD – Gabrovo – Care for Children with Disabilities Foundation;

- DCCCD – Russe – Russe Association for People with Intellectual Disabilities;

- DCCCD – Russe – Child and Space Association;

- DCCCD – Russe – Caritas Russe Catholic Organisation;

- DCCCD – Slivo Pole - Russe Association for People with Intellectual Disabilities;

- DCCCD – Sevlievo – International Social Service Bulgaria Foundation;

- DCCCD – Pleven – Municipality in partnership with BAPID Association;

- DCCCD – Karlovo – Sonic Start Ltd.;

- DCCCD – Plovdiv – Future for Bulgaria Foundation – Plovdiv Branch;

- DCCCD – Sofia – International Social Service Bulgaria Foundation;

- DCCCAD – Dryanovo – Association for People with Mental Health Problems and Intellectual Disabilities;

- DCCCAD – Lovech – Protection Association – Lovech.

- Organisations supporting the process

Over the review period, the activities for deinstitutionalisation of childcare were implemented again in strong cooperation with UNICEF and the NGO sector.

The National Network for Children (NNC) is an association of NGOs working with children and families across the country. The Network supports the childcare deinstitutionalisation process in the country from the onset. The National Network is a member of Coalition “Childhood 2015” whose main aim is to ensure the sustainable development of deinstitutionalisation with a focus on development of community-based individual care for every child who is a process actor. A representative of the Network was also on the team that prepared the present report.

* The main contribution of NGOs in the field of childcare deinstitutionalisation over the review period is presented in an annex to the report.

- D. Independent evaluation of the deinstitutionalisation process

A quick review and assessment of the implementation of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria” and its Action Plan was commissioned by UNICEF Bulgaria to an independent international consultant on the basis of a decision of the Interdepartmental Working Group for management and coordination of the deinstitutionalisation process. The purpose of the review is to take stock of the current situation and to strengthen the implementation of the Vision in the immediate period through to end of 2015 and in the medium-term period 2015-2020. The Bulgarian Government is recommended to draft a new Action Plan for implementation of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic of Bulgaria”. It should be prepared in extensive consultation with the professional and the NGO community, to keep the focus on deinstitutionalisation of care services and closure of all institutions for children, but with greater emphasis given to whole system reform, including prevention and family support.

* A summary of the specific proposals and recommendations is presented in an annex to this report.

# 3. Main conclusions and recommendations

  - Updating the map of supporting services, taking into account the existing ones and their interrelation. The practice of the existing centres for family-type accommodation and protected homes shows that care could not be individualised if there is lack of a set of community-based services. This creates a real risk of duplicating the practices of specialised institutions which could lead to transformation of the new into small institutions;

  - Enhanced preparation and support for the CFTA and PH teams in view of addressing the problems, providing better care to children and reducing turnover;

  - Encouraging the building up of expertise in view of setting up a system for support, partnership and exchange of good practices and information among the teams operating in the new services;

  - Supporting and encouraging continuous training and supervision of the teams operating in the new services;

  - Timing the deadlines for implementation of the Action Plan projects. Due to the different building rates of the new services, the implementation of the operation “Don’t Leave a Child Out” was delayed by approximately one year. Component 2 was extended by 1 year, submission of a request for extension of Component 1 is pending;

  - Updating the (or drafting a new) Action Plan upon completion of the projects from the   2007-2014 programming period, given the need to reformulate the objectives set therein;

  - Designing a clear and concrete financial mechanism for transferring the maintenance money from the specialised institutions to be closed to the new residential services;

  - Improving the access to health services and sustained commitment of health system for all children;

  - Designing model/s for the provision of integrated health and social services for children which are legally regulated and supported with the necessary financial resources. For successful implementation of the model/models the mental health system (within the health system) needs to upgrade the local capacity for addressing adequately the mental health care needs of the children and youths from the specialised institutions;

  - Procuring resources for building and maintaining community-based supporting services, and for enhancing the capacity of the existing ones, in keeping with the needs of the children and youths to be placed in the new residential services. There is a need of day care services, protected homes and inclusive education services at the kindergartens and schools in every region, in cooperation with the resource centres in the school system, and also opportunities have to be created to support the families of children with disabilities. If these two conditions are not fulfilled, there is high risk that the new residential services may duplicate the institutional model of care;

  - Systematic work by the child protection system and the social service providers with the parent of children at risk, including children with disabilities placed in residential services;

  - A need to review and update the Action Plan to the National Health Strategy;

  - The closure of HMSCC pursuant to the national and European policies should be synchronised with the restructuring of these homes from providers of residential services for babies and children into centres / complexes for medical and social rehabilitation and integration of children with disabilities and chronic illnesses aged 0 – 18;

  - A need of active involvement of a team of professionals – experts from MLSP, SAA, SACP, MF and external experts /Interdepartmental Working Group/ in designing the final variant of the financial standard for foster care. The finalised financial standard will provide the basis for changing the legal regulation of the foster care social service and establishing it as an activity delegated by the state;

  - Greater publicity of the child care deinstitutionalisation process;

  - Building a common communication space for all process stakeholders;

  - Provision on a regular basis of up-to-date information to MES on the launch of the activity in the FTPC and protected homes built in view of smooth inclusion of the children in the curriculum on the ground and for the planning and appointment of different number of specialists;

  - Lack of correspondence between the timeframes for placement and the timeframes under the education laws when timing the transfer of the children from the homes for children into CFTA in other municipalities their enrolment in new schools – the transfer 1 month before the end of the school year makes it impossible to present the results of their education for the respective school year and sometimes prevents them from successful completion of the school year. This is obviously not in the interest of the children.

А. Updating the Action Plan – shared approaches and principles

The following themes should be included in the future update of the Action Plan:

1. There is a need of change with focus on prevention and family support in keeping with the UN Guidelines on the Alternative Care for Children, continuing however the closure of specialised institutions enhancing the capacity of the new community-based services. A need of a social service working with the children and families at risk and offering them complex support. The early intervention services are seen mainly in terms of maternal and child health services rather than the multidisciplinary services needed to focus on early childhood development.

2. Guaranteeing the right of children to family environment is a priority of the child care reform. Efforts are focused on improving the good and responsible parenting skills and changing the attitude to the child.

3. Study the quality standards applied in the country to social services to inform legislative changes and future improvements in the social sphere. Designing indicators for the quality of social services could be a prerequisite for the development of quality monitoring and control systems to be implemented for the process of transition, as well as for the services resulting from the transition, with clear focus on meeting the needs of users.

4. Early intervention for disabilities through training of the medical staff, direct work with the children with disabilities and their families from the birth of the child which includes in addition to rehabilitation in the special centres set up under the project also activities for counselling, training, mobile work with the child at home.

5. Informing decision making through professional and detailed individual assessments of the needs of the children placed in institutional care, conferences on cases and regular reviews.

6. Successful “gate control” to prevent the placement of children in HMSCC.

7. Building the infrastructure and training workforce for the community-based services (residential and non-residential).

8. Regional analyses and regional social service development strategies which forecast the need of services and could be used for the purposes of planning and monitoring.

Support for the new social services

The need of continuous capacity building of the staff employed in the new social services persists. The teams’ under preparedness at the start of the CFTA and PH services and the related high turnover pose great challenges to the smooth development of the deinstitutionalisation process.

Financing

The responsible institutions need to take steps for more flexible financing of social services.

There is lack of a financial mechanism guaranteeing the reallocation of funds from the existing specialised institutions to the new services developed under the projects.

The uniform financial standard for provision of the foster care service is not a fact yet.

Integrated services

There is a need to design models for provision of integrated health and social services for children with severe disabilities who need medical care as a matter of priority, and for children with mental disorders.

Coordination and communication

In order to ensure better coordination and communication in the deinstitutionalisation process, it is necessary to concentrate on the increasing interaction between all administrative structures implementing projects under HRD OP, RD OP and RDP.

Information and publicity

Attracting the local communities and increasing citizen participation in the processes of support and social inclusion of the children from the specialised institutions.

Information and publicity on the problems of the children deprived of parental care, with focus on abandonment risk prevention, early intervention and family support.

B. Sequencing of the OP activities for the next programming period

Process management and coordination at national, regional and local level

The implementation of activities for deinstitutionalisation of children in Bulgaria requires a deeper and coherent approach, better targeting of the available resources and continuity.

To that end, different operations which are complementary and follow one after the other need to be laid down for implementation in the upcoming programming period in order to ensure effectiveness, continuity, sustainability, involvement of a wide circle of actors and strong institutional commitments again for the implementation of individual sector policies related to the deinstitutionalisation process.

In the period 2007-2013, following the guidelines of the National Strategy “Vision for Deinstitutionalisation of Children in the Republic Bulgaria”, projects for the deinstitutionalisation of children were supported from the European Social Fund under Human Resources Development Operational Programme 2007-2013. The process and the measures implemented along these lines to date will be continued and implemented also in the new programming period 2014-2020. The policy for supporting children and families will be focused on introducing a new approach in child care aiming at prevention, early intervention, support for the families and provision of family or close to family environment for every Bulgarian child.

The key tool for achieving these purposes is the deinstitutionalisation of child care. This is one of the major lines of action to be financed according to the strategy of Human Resources Development Operational Programme 2014-2020, together with targeted support for replacing the institutional model of care for elderly people and people with disabilities by community-based services.

The measures to be implemented within the second axis of the operational programme will contribute to realising initiatives aimed at early intervention and prevention of child abandonment and placement in specialised institutions, early childhood development services and measures to procure the necessary resources for abolishing the institutional model of child care, in accordance with the main objective of the National Strategy for the Child 2008-2018 which is to ensure effective exercise of their rights and improved quality of life of children as a condition for their free and full personal development.

Support for the process of deinstitutionalisation of social services for children and adults is envisaged under Priority Axis 4 “Regional Social Infrastructure” of Operational Programme “Regions in Growth” 2014-2020 with committed financial resource at EUR 50 857 681 or almost 100 million BGN. Eligible in respect of the services for children are construction works, repair, reconstruction of centres providing services for children at risk, as well as supply of equipment and furniture for the buildings/premises within their overall renovation. The financing of infrastructure measures for deinstitutionalisation of children and youths will be wholly supported by RD OP 2014-2020, in contrast to the previous programming period when it was also supported by the Rural Development Programme. In the programming period 2007-2013, funds for construction of supporting services (day care centre and centre for social rehabilitation and integration, etc.) for the children with disabilities who will leave the specialised institutions were not committed. Funds for this purpose are committed in the next programming period 2014-2020 with a view to ensuring full inclusion of the children and creating environment as near as possible to family environment, as well as integrated community-based services. In that light, active work is needed on preparing and approving the National Service Map for supporting services. For deinstitutionalisation of the children from the homes for children deprived of parental care, there is a need to prepare and approve an analysis of the needs of additional investments in infrastructure related to the closure of HCDPC. Given the limited resource for deinstitutionalisation under RD OP 2014-2020 (100 million BGN for children and adults), the Ministry of Labour and Social Policy as the institution responsible for the implementation of adequate and targeted social policy should take decision on the focus of the interventions:

- Continuing (and possibly closing) the deinstitutionalisation process launched for the children with disabilities (and HMSCC) by building supporting services in keeping with the National Service Map for supporting services.

- Proceeding to deinstitutionalisation of the children from the homes for children deprived of parental care by preparing analyses and approving the respective National Service Maps.

Attachments:

- Information on each one of the Action Plan projects

- Quick review and assessment of the implementation of the Action Plan

- Attachments on the contribution of NGOs

Abbreviations used:

BAPID – Bulgarian Association for People with Intellectual Disabilities

CC – Crisis Centre

CFC – Centre for Family Consultation

CFTA – Center for Family-type Accommodation

CM – Coordination Mechanism

CSC – Community Support Centre

CSRI – Centre for Social Rehabilitation and Integration

CWCS – Centre for Working with Children in the Street

DCC – Day Care Centre

DCCCD – Day Care Centre for Children with Disabilities

DCCCAD – Day Care Centre for Children and Adults with Disabilities

DI - Deinstitutionalisation

EC – European Commission

EU – European Union

HHC – Hope and Homes for Children, Bulgaria

HCDPC – Homes for Children Deprived of Parental Care

HCPD – Home for Children with Physical Disabilities

HMSCC – Home for Medical and Social Care for Children Aged 0 – 3

HRD OP – Human Resources Development Operational Programme

IC – Invalidity Committee

MAF – Ministry of Agriculture and Food

MBU – Mother and Baby Unit

MES – Ministry of Education and Science

MF – Ministry of Finance

MH – Ministry of Health

MJ – Ministry of Justice

MLSP – Ministry of Labour and Social Policy

MRD – Ministry of Regional Development

NAMRB – National Association of Municipalities in the Republic of Bulgaria

NDU – National Deinstitutionalisation Unit

NGOs – Non-Governmental Organisations

NNC – National Network for Children

PIU – Project Implementation Unit(s)

PH – Protected Home

RDP – Rural Development Programme

RD OP – Regional Development Operational Programme

RDSA – Regional Directorates for Social Assistance – territorial structures of the Social Assistance Agency at the regional level

RHI – Regional Health Inspectorate

RIE – Regional Inspectorate of Education

RTD – Regional Team on Deinstitutionalisation

SAA – Social Assistance Agency

SACP – State Agency for Child Protection

SAD/CPD/PDSS – Social Assistance Directorates and the Child Protection Departments and People with Disabilities and Social Services Departments at local level

SFA – State Fund Agriculture

SFF – Specialised Foster Families

SHC – Shelter for Homeless Children

TA OP – Technical Assistance Operational Programme

On 1 July 2014 – beyond the review period covered by the present monitoring report – RICID Iskra was closed with an act of the Executive Director of SAA.